## MDR
PROJECT 1
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 2021-05-28
No |  |  | Total Manhour | Weight Factor | DOC.QTY | Issued for Review (IFR) | [7 empty] | Issued for Approval (IFA/As-Built) | [7 empty] | Discipline | Remark
| Doc.Number | Document Title
[6 empty] | Plan | Submit |  |  | Return |  |  |  | Plan | Submit |  |  | Return
[7 empty] | Actual | Transmittal | Status | Plan | Actual | Transmittal | Status |  | Actual Date | Transmittal | Status | Plan | Actual | Transmittal | Status
A | As Built - Kurus Station |  | 1294.276 | 34.85% | 37
2 | KRS-G-RE-001 | Site Survey Report (include Site Survey) | 572 | 15.4% | 1 | 2020-11-26 | 2020-12-30 | 004 | IFR | 2020-12-31 | 2021-02-05 | 069 | AWC | 2021-01-03 | 2020-12-31 | 2021-03-01 | 009 | 2021-01-10 | 2021-03-04 | 106 | AWC | General
3 | KRS-R-PF-001 | Process Flow Diagram (PFDs) | [19 empty] | Process
| KRS-R-PF-001 | PFD Kurus Gas Station | 9.45 | 0.2545% | 1 | 2021-03-19 | 2020-12-31 | 005 | IFR | 2021-04-02 | 2021-01-08 | 012 | NA | 2021-04-19 | 2021-04-19 | 019 | AsB | 2021-05-03 | 2021-05-03 | 232 | APP | Process
| KRS-R-PF-002 | PFD Kurus Gas Station | 9.45 | 0.2545% | 1 | 2021-03-19 | 2020-12-31 | 005 | IFR | 2021-04-02 | 2021-01-08 | 012 | NA | 2021-04-19 | 2021-04-19 | 019 | AsB | 2021-05-03 | 2021-05-03 | 232 | APP | Process
| KRS-R-PF-003 | PFD Kurus Gas Station | 9.45 | 0.2545% | 1 | 2021-03-19 | 2020-12-31 | 005 | IFR | 2021-04-02 | 2021-01-08 | 012 | NA | 2021-04-19 | 2021-04-19 | 019 | AsB | 2021-05-03 | 2021-05-03 | 232 | APP | Process
4 | KRS-R-PI-001 | Process and Instrumentation Diagram (PIDs) | [19 empty] | Process
| KRS-R-PI-001 | PID HP Test Prod Manifold | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 |  | 2021-05-05 | NA | Process
| KRS-R-PI-002 | PID LP Test Prod Manifold TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-003 | PID MP Prod Separator TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-004 | PID LP Prod Separator TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-005 | PID HP Prod Separator TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 |  | 2021-05-05 | NA | Process
| KRS-R-PI-006 | PID LP Test Separator TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-007 | PID LP Suction Scrubber TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-008 | PID LP Compressor TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-009 | PID MP Suction Scrubber TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-010 | PID MP Compressor TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-011 | PID HP Discharge Scrubber TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-012 | PID 16 Gas Pig Launcher to RBW & Liquid Pig Receiver | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-013 | PID Gas Flare System Kurus Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2021-03-05 | 010 | IFR | 2021-03-19 | 2021-04-05 | 177 | AWC | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-014 | PID Liquid Header System Kurus Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2021-03-05 | 010 | IFR | 2021-03-19 | 2021-04-05 | 177 | AWC | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 |  | 2021-05-05 | NA | Process
| KRS-R-PI-015 | PID Fuel Gas System TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-016 | PID Liquid Scrubber -Ex Matra (KRS-MBF-113) TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-017 | PID Fire Fighting System TRS Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-018 | P&ID Liquid Scrubber (MBFT-108) Kurus Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2021-03-05 | 010 | IFR | 2021-03-19 | 2021-04-05 | 177 | AWC | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 |  | 2021-05-05 | NA | Process
| KRS-R-PI-019 | P&ID Condensate Tank (MBJT-106-107) And CTP Kurus Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2021-03-05 | 010 | IFR | 2021-03-19 | 2021-04-05 | 177 | AWC | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-020 | PID Piping System TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-021~1 | PID Gas Metering System TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-021~2 | P&ID Pig Receiver Launcher and Gas Metering Kurus Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2021-03-05 | 010 | IFR | 2021-03-19 | 2021-04-05 | 177 | AWC | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-024 | PID Fuel Gas Scrubber | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2021-03-05 | 010 | ReIFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-025 | PID Condensate Tank 5000 BBLS | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2021-03-05 | 010 | ReIFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-026 | PID Instrument Air Dryer Skid TRS Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2021-03-05 | 010 | ReIFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-028 | PID Crude Transfer Pump | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 |  | 2021-05-05 | NA | Process
| KRS-R-PI-029~1 | PID Pig Receiver from GKB TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-029~2 | PID Pig Receiver from GKB TRS Gas Station | [11 empty] | 2021-04-20 | 2021-04-21 | 020 | AsB |  | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-030 | PID Lube Oil | [16 empty] | 2021-05-05 | 241 | AWC | Process
| KRS-R-PI-031 | PID HP Gas Scrubber KRS-MBF-110 TRS Gas Station | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-032 | PID HP Production Separator (New) | 12.1221 | 0.3264% | 1 | 2021-03-05 | 2020-12-30 | 004 | IFR | 2021-03-19 | 2021-02-02 | 066 | NA | 2021-04-20 | 2021-04-21 | 020 | AsB | 2021-05-04 | 2021-05-05 | 241 | APP | Process
| KRS-R-PI-033 | PID Coolant System Kurus Station | [16 empty] | 2021-05-05 | 241 | AWC | Process
5 | KRS-R-SF-001 KRS-R-CH-001 | SAFE Chart | 30.24 | 0.8142% | 1 | 2021-03-15 | 2020-12-31 | 005 | IFR | 2021-03-29 |  | 2021-01-08 | NA | 2021-04-30 | 2021-05-21 | 027 | AsB | 2021-05-21 |  |  |  | Process
6 | KRS-P-PL-001 | Plot Plan | 112.266 | 3.023% | 1 | 2021-03-15 | 2020-12-31 | 006 | IFR | 2021-03-29 | 2021-01-18 | 021 | AWC | 2021-03-16 | 2021-03-16 | 013 | IFA | 2021-03-23 | 2021-05-03 | 232 | APP | Piping
7 | KRS-I-WI-001 | Wiring Connection Diagram | 173.124 | 4.662% | 1 | 2021-03-15 | 2020-12-23 | 003 | IFR | 2021-03-29 |  | 2020-12-31 | NA | 2021-04-30 |  |  |  | 2021-05-21 |  |  |  | Instrument
8 | KRS-I-CA-001 | Architecture Diagram | 26.756 | 0.7204% | 1 | 2021-03-15 | 2020-12-10 | 001 | IFR | 2021-03-29 | x | 2020-12-21 | NA | 2021-04-30 | 2021-05-19 | 026 |  | 2021-05-21 |  |  |  | Instrument
B | As Built - Siska Station |  | 1252.318 | 33.72% | 35
10 | SSK-G-RE-001 | Site Survey Report (include Site Survey) | 572 | 15.4% | 1 | 2020-12-03 | 2020-12-30 | 004 | IFR | 2020-12-17 | 2021-02-06 | 070 | AWC | 2020-12-31 | 2021-03-01 | 009 | IFA | 2021-01-07 | 2021-03-04 | 106 | AWC | General
11 | SSK-R-PF-001 | Process Flow Diagram (PFDs) | [19 empty] | Process
| SSK-R-PF-001 | PFD Siska Station | 12.6 | 0.3393% | 1 | 2021-03-15 | 2020-12-31 | 005 | IFR | 2021-03-29 |  | 2021-01-08 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PF-002 | PFD Siska Station | 12.6 | 0.3393% | 1 | 2021-03-15 | 2020-12-31 | 005 | IFR | 2021-03-29 |  | 2021-01-08 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PF-003 | PFD Siska Station | 12.6 | 0.3393% | 1 | 2021-03-15 | 2020-12-31 | 005 | IFR | 2021-03-29 |  | 2021-01-08 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
12 | SSK-R-PI-001 | Process and Instrumentation Diagram (PIDs) | [19 empty] | Process
| FRZ-R-PI-008 | PID New HP Discharge Scrubber at SKA Station | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-000 | Cover Sheet PID Siska Gas Station | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-001 | PID HP Test Prod Manifold | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-002 | PID LP Test Prod Manifold | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-003 | PID HP Prod Separator | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-004 | PID LP Prod Separator | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-005 | PID HP Test Separator | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-006 | PID LP Test Separator | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-007 | PID LP Suction Scrubber | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-010 | PID Pig Launcher Siska - Kurus | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-011 | PID Liquid Header to Flash Separator | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-012 | PID Flash Separator | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-013 | PID Instrument Air and Utility Air System | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-014 | PID Fuel Gas Scrubber | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-015 | PID Fire Water Ring | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-016 | PID Fire Fighting Pumps and Foam Package | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-017 | PID Crude Oil Tank (ABJSK-420 AB) | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-018 | PID Recover Pump | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-019 | PID Transfer Pumps PAXSK-331ABC | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-021 | PID LP Suction Scrubber V-05 | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-022 | PID Blowdown and Flare Header | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-023 | PID Genset 3512 | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-024 | PID MP Production Separator | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-025 | PID MP Scrubber | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-027 | PID HP Scrubber | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-028 | PID Drain System (PIT) | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
| SSK-R-PI-029 | PID Lube Oil | 12.18 | 0.328% | 1 | 2021-03-15 | 2020-12-31 | 004 | IFR | 2021-03-29 |  | 2021-01-26 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
13 | SSK-R-SF-001 | SAFE Chart | 30.24 | 0.8142% | 1 | 2021-03-15 | 2020-12-31 | 005 | IFR | 2021-03-29 |  | 2021-01-08 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Process
14 | SSK-P-PL-001 | Plot Plan | 112.266 | 3.023% | 1 | 2021-03-15 | 2020-12-31 | 006 | IFR | 2021-03-29 | 2021-01-18 | 021 | AWC | 2021-04-12 | 2021-04-01 | 016 | IFA (AsB) | 2021-04-19 |  | 2021-04-19 | NA | Piping
15 | SSK-I-WI-001 | Wiring Connection Diagram | 144.396 | 3.888% | 1 | 2021-03-15 | 2020-12-18 | 002 | IFR | 2021-03-29 |  | 2021-02-03 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Instrument
16 | SSK-I-CA-001 | Architecture Diagram | 26.756 | 0.7204% | 1 | 2021-03-15 | 2020-12-10 | 001 | IFR | 2021-03-29 |  | 2020-12-21 | NA | 2021-03-29 |  |  |  | 2021-04-05 |  |  |  | Instrument
C | As Built - Gn. Guntur Station |  | 1167.268 | 31.43% | 33
18 | GGT-G-RE-001 | Site Survey Report (include Site Survey) | 572 | 15.4% | 1 | 2021-02-12 | 2021-01-05 | 008 | IFR | 2021-02-26 | 2021-01-13 | 020 | NA | 2021-03-12 | 2021-03-01 | 009 | IFA | 2021-03-19 | 2021-03-04 | 106 | AWC | General
19 | GGT-R-PF-001 | Process Flow Diagram Gn. Guntur Station | 9.45 | 0.2545% | 1 | 2021-03-15 | 2020-12-31 | 006 | IFR | 2021-03-29 | 121 | 2021-01-05 | NA | 2021-04-26 | 2021-04-23 | 021 | IFA | 2021-05-10 | 2021-05-03 | 232 | APP | Process
20 | GGT-R-PI-001 | Process and Instrumentation Diagram (PIDs) | [19 empty] | Process
| GGT-R-PI-001 | PID HP Test Prod MP Prod Manifold | 10.08 | 0.2714% | 1 | 2021-03-15 | 2020-12-31 | 006 | Re-IFR | 2021-04-22 | 121 | 2021-01-05 | NA | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-002 | PID Piping to MP Test Prod Separator | 10.08 | 0.2714% | 1 | 2021-03-15 | 2020-12-31 | 006 | Re-IFR | 2021-04-22 | 121 | 2021-01-05 | NA | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-003 | PID LP Test Production Manifold | 10.08 | 0.2714% | 1 | 2021-03-15 | 2020-12-31 | 006 | Re-IFR | 2021-04-22 | 121 | 2021-01-05 | NA | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-004 | PID Tamanli MP Production Separator | 10.08 | 0.2714% | 1 | 2021-03-15 | 2020-12-31 | 006 | Re-IFR | 2021-04-22 | 121 | 2021-01-05 | NA | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-005 | PID MP Production Separator | 10.08 | 0.2714% | 1 | 2021-03-15 | 2020-12-31 | 006 | Re-IFR | 2021-04-22 | 121 | 2021-01-05 | NA | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-006 | PID LP Production Separator | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-007 | PID HP Test Separator | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-008 | PID MP Test Separator | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-009 | PID LP Test Separator | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-010 | PID LP Suction Scrubber | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-011 | PID LP Compressor | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-012 | PID MP Suction Scrubber | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-013 | PID MP Compressor | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-014 | PID HP Discharge Scrubber | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-015 | PID Future Metering - Pig Launcher | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-016 | PID Liquid Piping System | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-017 | PID Air Distribution System | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | NA | Process
| GGT-R-PI-018 | PID Fire Fighting System | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | NA | Process
| GGT-R-PI-019 | PID Flare System | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| GGT-R-PI-020 | PID Storage Tank 5000-200 BBLS | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-021 | PID Horizontal Test Separator | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-022 | PID Crude Transfer Pump | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-023 | PID Utilities Water System | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-024 | PID Fuel Gas System | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | AWC | Process
| GGT-R-PI-025 | PID Lube Oil | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | NA | Process
| TML-R-PI-010 | PID Pig Launcher - Receiver Tamanli | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
| TML-R-PI-012 | PID Slug Catcher Tamanli | 10.08 | 0.2714% | 1 | 2021-03-15 | 2021-04-12 | 017 | IFR | 2021-04-22 | x |  |  | 2021-05-04 | 2021-04-28 | 022 | AsB | 2021-05-18 | 2021-06-03 | unoff | APP | Process
21 | GGT-R-SF-001 GGT-R-CH-001 | SAFE Chart | 30.24 | 0.8142% | 1 | 2021-03-15 | 2020-12-31 | 005 | IFR | 2021-03-29 | 2021-04-23 | 213 | AWC | 2021-04-12 | 2021-05-21 | 027 | AsB | 2021-04-26 |  |  |  | Process
22 | GGT-P-PL-001 | Plot Plan | 112.266 | 3.023% | 1 | 2021-03-15 | 2020-12-31 | 006 | IFR | 2021-03-29 | 2021-01-18 | 021 | AWC | 2021-04-12 | 2021-03-10 | 011 | IFA | 2021-05-03 |  | 2021-05-04 | NA | Piping
23 | GGT-I-WI-001 | Wiring Connection Diagram | 144.396 | 3.888% | 1 | 2021-03-15 | 2020-12-23 | 003 | IFR | 2021-03-29 |  | 2020-12-31 | NA | 2021-04-12 |  |  |  | 2021-04-26 |  |  |  | Instrument
24 | GGT-I-CA-001 | Architecture Diagram | 26.756 | 0.7204% | 1 | 2021-03-15 | 2020-12-10 | 001 | IFR | 2021-03-29 |  | 2020-12-31 | NA | 2021-04-12 | 2021-04-29 | 023 | IFA | 2021-04-26 |  | 2021-05-06 | NA | Instrument
|  | Total | 3713.862 | 100% | 105
[22 empty] | S-Curve Data | S-Curve Data
[22 empty] | Plan | Plan
[22 empty] | Plan Cumm | Plan Cumm
KRS-G-RE-001
SSK-G-RE-001
GGT-G-RE-001
Formulas:
Return = [Issued for Approval (IFA/As-Built)]+7
Return = [Issued for Review (IFR)]+14
Issued for Approval (IFA/As-Built) = [Return]+14
Issued for Approval (IFA/As-Built) = [Issued for Review (IFR)]+14
Note on H12: Zata Atsarina: Re-IFR 19 Mar 21
Note on H13: Zata Atsarina: Re-IFR 19 Mar 21
Note on H14: Zata Atsarina: Re-IFR 19 Mar 21
Note on H16: asani: 05-Mar-21
Note on I16: asani: 010
Note on J16: asani: Re-IFR
Note on H17: asani: 05-Mar-21
Note on I17: asani: 010
Note on J17: asani: Re-IFR
Note on H18: asani: 05-Mar-21
Note on I18: asani: 010
Note on J18: asani: Re-IFR
Note on H19: asani: 05-Mar-21
Note on I19: asani: 010
Note on J19: asani: Re-IFR
Note on H20: asani: 05-Mar-21
Note on I20: asani: 010
Note on J20: asani: Re-IFR
Note on H21: asani: 05-Mar-21
Note on I21: asani: 010
Note on J21: asani: Re-IFR
Note on H22: asani: 05-Mar-21
Note on I22: asani: 010
Note on J22: asani: Re-IFR
Note on H23: asani: 05-Mar-21
Note on I23: asani: 010
Note on J23: asani: Re-IFR
Note on H24: asani: 05-Mar-21
Note on I24: asani: 010
Note on J24: asani: Re-IFR
Note on H25: asani: 05-Mar-21
Note on I25: asani: 010
Note on J25: asani: Re-IFR
Note on H26: asani: 05-Mar-21
Note on I26: asani: 010
Note on J26: asani: Re-IFR
Note on H27: asani: 05-Mar-21
Note on I27: asani: 010
Note on J27: asani: Re-IFR
Note on H30: asani: 05-Mar-21
Note on I30: asani: 010
Note on J30: asani: Re-IFR
Note on H31: asani: 05-Mar-21
Note on I31: asani: 010
Note on J31: asani: Re-IFR
Note on H32: asani: 05-Mar-21
Note on I32: asani: 010
Note on J32: asani: Re-IFR
Note on H35: asani: 05-Mar-21
Note on I35: asani: 010
Note on J35: asani: Re-IFR
Note on H36: asani: 05-Mar-21
Note on I36: asani: 010
Note on J36: asani: Re-IFR
Note on H41: asani: 05-Mar-21
Note on I41: asani: 010
Note on J41: asani: Re-IFR
Note on H42: asani: 05-Mar-21
Note on I42: asani: 010
Note on J42: asani: Re-IFR
Note on H45: asani: 05-Mar-21
Note on I45: asani: 010
Note on J45: asani: Re-IFR
Note on H46: asani: 05-Mar-21
Note on I46: asani: 010
Note on J46: asani: Re-IFR
Note on H48: Zata Atsarina: Re-IFR 19 Apr'21
Note on P49: Zata Atsarina: Re-submit 1 Apr 21 Re-submit 30 apr 21
Note on H50: Zata Atsarina: Re-IFR 13 Apr'21
Note on H51: Zata Atsarina: Re-IFR 19 Mar 21
Note on H91: asani: 01-Mar-21
Note on I91: asani: 009
Note on J91: asani: Re-IFR
Note on H94: Zata Atsarina: Re-IFR 12 Apr'21
Note on H95: Zata Atsarina: Re-IFR 12 Apr'21
Note on H96: Zata Atsarina: Re-IFR 12 Apr'21
Note on H97: Zata Atsarina: Re-IFR 12 Apr'21
Note on H98: Zata Atsarina: Re-IFR 12 Apr'21
Note on H123: Zata Atsarina: Re-IFR on 3 May 21
Note on H124: Zata Atsarina: Re-IFR 14 Apr'21