## MDR
PROJECT 2
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
No |  |  |  | Total Manhour | Weight Factor | DOC.QTY | Issued for Review (IFR) | [7 empty] | Issued for Approval (IFA) | [7 empty] | Discipline | Remark
| Doc.Number | Document Title
[7 empty] | Recovery Date | Submit |  |  | Return |  |  |  | Recovery Date | Submit |  |  | Return
[8 empty] | Actual | Transmittal | Status | Recovery | Actual | Transmittal | Status |  | Actual Date | Transmittal | Status | Recovery | Actual | Transmittal | Status
A | SITE VISIT |  | 170 | 288 | 9.99% | 1 | [16 empty] | General
|  | Site Visit Report | [20 empty] | General
1 | KRS-R-RE-001 | Site Visit Report (include Site Visit Activity) | 170 | 288 | 9.99% | 1 | 2021-01-27 | 2020-12-30 |  |  | 2021-02-10 | 2020-12-28 |  |  | 2021-05-21 | 2020-12-30 |  |  | 2021-05-28 |  | 2021-01-18 | NA | General
B | PROCESS |  | 815 | 920 | 31.91% | 204 | [16 empty] | Process
|  | Design Basis and Philosophy | [20 empty] | Process
2 | KRS-R-DB-001 | Project Design Basis | 31 | 128 | 4.44% | 1 | 2021-04-23 | 2020-12-30 |  | Re-IFR | 2021-05-07 |  | unoff | NA | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Process
|  | Study and Calculation | [20 empty] | Process
3 | KRS-R-CC-001 | Process Simulation Report | 58 | 116 | 4.024% | 1 | 2021-03-19 | 2020-12-29 |  |  | 2021-04-02 | 2021-02-11 |  | AWC | 2021-04-16 | 2021-04-08 |  |  | 2021-04-30 | 2021-04-21 |  | APP | Process
4 | KRS-R-CC-002 | Vessel and Seperator Sizing and Study Report (directly to IFA) | 34 | 56 | 1.942% | 1 | 2021-03-19 | 2020-12-30 |  |  | 2021-04-02 | 2021-03-05 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-04-27 |  | AWC | Process
5 | KRS-R-SY-001 | Flare System Line Study | 64 | 16 | 0.555% | 1 | 2021-05-07 | 2021-04-05 |  |  | 2021-05-07 | 2021-04-27 |  | AWC | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Process
6 | KRS-R-SY-002 | Relief and Blowdown Study Report | 106 | 116 | 4.024% | 1 | 2021-03-26 | 2020-12-31 |  |  | 2021-04-09 | 2021-03-15 |  | AWC | 2021-04-23 | 2021-05-03 |  |  | 2021-04-30 |  |  |  | Process
7 | KRS-R-CC-003 | Calculation for Flare KO Drum Pump Sizing | 28 | 86 | 2.983% | 1 | 2021-03-19 | 2020-12-31 |  |  | 2021-04-02 | 2021-03-03 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-06 | 243 | APP | Process
8 | KRS-R-SY-003 | Utility (IA, Fuel Gas, Purge Gas) Consumption Study | 48 | 16 | 0.555% | 1 | 2021-04-23 | 2021-01-29 |  |  | 2021-05-07 | 2021-02-11 |  | AWC | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Process
|  | List | [20 empty] | Process
9 | KRS-R-LI-001 | Line List | 22 | 12 | 0.4162% | 1 | 2021-05-10 | 2021-03-19 |  | Re-IFR | 2021-05-14 |  | 2021-03-30 | NA | 2021-05-28 |  |  |  | 2021-06-04 |  |  |  | Process | unofficial review
10 | KRS-R-LI-002 | Tie-In Point List | 22 | 12 | 0.4162% | 1 | 2021-04-12 | 2021-03-29 |  |  | 2021-04-26 | 2021-03-31 |  | AWC | 2021-05-10 |  |  |  | 2021-05-17 |  |  |  | Process
|  | Drawing | [20 empty] | Process
11 | KRS-R-PF-001 | PFD Semangka Gas Station (directly to IFA) | 18 | 24 | 0.8325% | 1 | 2021-03-19 | 2020-12-29 |  |  | 2021-04-02 | 2021-02-15 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-03 |  | AWC | Process
12 | KRS-R-HMB-001 | Heat and Material Balance | 52 | 100 | 3.469% | 1 | 2021-03-19 | 2020-12-29 |  |  | 2021-04-02 | 2021-02-15 |  | AWC | 2021-04-16 | 2021-04-12 |  |  | 2021-04-30 | 2021-04-29 |  | APP | Process
13 | KRS-R-PI-002 | P&ID Test Production Manifold | 8.5 | 6 | 0.2081% | 2 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-10 |  | APP | Process
14 | KRS-R-PI-004 | P&ID LP Production Separator | 14 | 12 | 0.4162% | 3 | 2021-03-19 | 2020-12-31 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
15 | KRS-R-PI-007 | P&ID LP Suction Scrubber | 8.5 | 6 | 0.2081% | 4 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
16 | KRS-R-PI-009 | P&ID MP Suction Scrubber MBFT-106 | 28 | 24 | 0.8325% | 5 | 2021-03-19 | 2020-12-31 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
17 | KRS-R-PI-010 | P&ID MP Compressor | 8.5 | 6 | 0.2081% | 6 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
18 | KRS-R-PI-011 | P&ID Discharge Scrubber MBFT-107 | 28 | 24 | 0.8325% | 7 | 2021-03-19 | 2020-12-31 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
19 | KRS-R-PI-012 | P&ID Gas Pig Launcher Liquid Pig Receiver | 8.5 | 6 | 0.2081% | 8 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
20 | KRS-R-PI-013 | P&ID Gas Flare System | 8.5 | 6 | 0.2081% | 9 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
21 | KRS-R-PI-014 | P&ID Liquid Header System | 8.5 | 6 | 0.2081% | 10 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
22 | KRS-R-PI-015 | P&ID Fuel Gas System | 8.5 | 6 | 0.2081% | 11 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
23 | KRS-R-PI-017 | P&ID Fire Fighting System | 8.5 | 6 | 0.2081% | 12 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
24 | KRS-R-PI-019 | P&ID Condensate Tank and CTP | 17 | 12 | 0.4162% | 13 | 2021-03-19 | 2020-12-31 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
25 | KRS-R-PI-020 | P&ID Piping System | 8.5 | 6 | 0.2081% | 14 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
26 | KRS-R-PI-021 | P&ID Gas Metering System | 8.5 | 6 | 0.2081% | 15 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
27 | KRS-R-PI-025 | P&ID Condensate Tank 5000 BBLS | 17 | 12 | 0.4162% | 16 | 2021-03-19 | 2020-12-31 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
28 | KRS-R-PI-026 | P&ID Instrument Air Dryer Skid | 8.5 | 6 | 0.2081% | 17 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
29 | KRS-R-PI-029 | P&ID Pig Receiver Siska - Kurus and Komeng | 8.5 | 6 | 0.2081% | 18 | 2021-03-19 | 2021-03-03 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
30 | KRS-R-PI-031 | P&ID LP Production Separator KRS - MBD - 110 | 14 | 12 | 0.4162% | 19 | 2021-03-19 | 2020-12-31 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
31 | KRS-R-PI-032 | P&ID HP Production Separator | 28 | 24 | 0.8325% | 1 | 2021-03-19 | 2020-12-31 |  |  | 2021-04-02 | 2021-03-10 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 | 2021-05-07 |  | APP | Process
32 | KRS-R-UF-001 | UFD for Fuel Gas Distribution | 28 | 12 | 0.4162% | 1 | 2021-03-19 | 2021-03-05 |  |  | 2021-04-02 | 2021-03-12 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-04-27 |  | AWC | Process
33 | KRS-R-UF-002 | UFD for IA/UA Distribution | 28 | 17 | 0.5897% | 1 | 2021-03-19 | 2021-03-05 |  |  | 2021-04-02 | 2021-03-12 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-04-27 |  | AWC | Process
34 | KRS-R-UF-003 | UFD for Flare and Vent Distribution | 28 | 17 | 0.5897% | 1 | 2021-03-19 | 2021-03-05 |  |  | 2021-04-02 | 2021-03-12 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-04-27 |  | AWC | Process
C | PROCESS SAFETY |  | 222 | 160 | 5.55% | 3 | [16 empty] | ProSaf
|  | Study and Calculation | [20 empty] | ProSaf
35 | KRS-F-SY-001 | Study for Flare Radiation and Dispersion | 62 | 100 | 3.469% | 1 | 2021-03-19 | 2020-12-17 |  | Re-IFR | 2021-04-02 | 2021-03-23 | unoff | APP | 2021-04-16 | 2021-03-29 |  |  | 2021-04-30 |  |  |  | ProSaf
36 | KRS-F-CC-001 | Calculation for Fire Water Demand | 100 | 30 | 1.041% | 1 | 2021-03-04 | 2021-02-02 |  |  | 2021-03-18 | 2021-02-15 |  | AWC | 2021-04-01 | 2021-03-17 |  |  | 2021-04-15 | 2021-03-23 | unoff | APP | ProSaf
37 | KRS-F-RE-001 | HAZOP and HAZID Close-Out Report | 60 | 30 | 1.041% | 1 | 2021-04-23 |  |  |  | 2021-05-07 |  |  |  | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | ProSaf
D | MECHANICAL |  | 96 | 48 | 1.665% | 3 | [16 empty] | Mechanical
|  | Datasheet | [20 empty] | Mechanical
38 | KRS-M-DS-001 | Datasheet for Flare KO Drum | 22 | 16 | 0.555% | 1 | 2021-03-29 | 2020-12-30 |  |  | 2021-04-12 | 2021-01-18 |  | AWC | 2021-04-26 | 2021-03-15 |  |  | 2021-05-10 | 2021-03-23 |  |  | Mechanical
39 | KRS-M-DS-002 | Datasheet for Flare KO Drum Pump and Pit Sum Pump | 22 | 16 | 0.555% | 1 | 2021-03-29 | 2020-12-30 |  |  | 2021-04-12 | 2021-03-23 |  | AWC | 2021-04-26 | 2021-05-07 |  |  | 2021-05-10 |  |  |  | Mechanical
40 | KRS-M-DS-003 | Datasheet for Flare Tip and Ignition System Package | 52 | 16 | 0.555% | 1 | 2021-03-29 | 2020-12-30 |  |  | 2021-04-12 | 2021-01-18 |  | AWC | 2021-04-26 | 2021-03-15 |  |  | 2021-05-10 |  | 2021-03-23 | NA | Mechanical
E | PIPING |  | 328 | 328 | 11.38% | 9 | [16 empty] | Piping
|  | Datasheet | [20 empty] | Piping
41 | KRS-P-DS-001 | Datasheet for Manual Valve | 34 | 34 | 1.179% | 1 | 2021-03-26 | 2020-12-30 |  |  | 2021-04-09 | 2021-03-31 |  | AWC | 2021-04-23 | 2021-04-26 |  |  | 2021-05-07 |  |  |  | Piping
42 | KRS-P-DS-002 | Datasheet and List of Piping Specialty Item | 34 | 34 | 1.179% | 1 | 2021-03-26 | 2020-12-30 |  |  | 2021-04-09 | 2021-03-31 |  | AWC | 2021-04-23 | 2021-04-26 |  |  | 2021-05-07 |  |  |  | Piping
|  | Drawing | [20 empty] | Piping
43 | KRS-P-PL-001 | Equipment Layout for Flare System**** (Direct Submission to IFA) | 12 | 12 | 0.4162% | 1 | 2021-03-26 | 2020-12-18 |  |  | 2021-04-09 | 2021-01-07 |  | AWC | 2021-04-23 | 2021-03-15 |  |  | 2021-05-07 | 2021-03-31 |  | AWC | Piping
new | KRS-P-GA-001 | Piping General Arrangement |  |  |  | 1 | 2021-04-16 | 2021-03-22 |  |  |  | 2021-04-22 |  | AWC | 2021-04-30 | 2021-05-07 |  |  | 2021-05-21 |  |  |  | Piping
44 | KRS-P-PP-001 | Piping Layout for Flare System | 80 | 80 | 2.775% | 1 | 2021-04-30 | 2020-12-29 |  |  | 2021-05-07 |  | 2021-01-26 | NA | 2021-05-21 | 2021-05-07 |  |  | 2021-06-04 |  |  |  | Piping
45 | KRS-P-IS-001 - 029 | Isometric Drawing for Flare System | 80 | 80 | 2.775% | 1 | 2021-05-07 | 2020-12-30 |  |  | 2021-05-07 |  | 2021-02-15 | NA | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Piping
46 | KRS-P-PS-001 | Pipe Support Drawing for Flare System | 24 | 24 | 0.8325% | 1 | 2021-04-09 | 2020-12-17 |  |  | 2021-04-23 | 2021-01-22 |  | AWC | 2021-05-07 | 2021-03-15 |  |  | 2021-05-21 |  | 2021-03-31 | NA | Piping
|  | Drawing | [20 empty] | Piping
47 | KRS-P-MT-001 | MTO for Piping Bulk | 36 | 36 | 1.249% | 1 | 2021-04-09 | 2020-12-30 |  |  | 2021-04-23 | 2021-04-22 |  | AWC | 2021-05-07 |  |  |  | 2021-05-21 |  |  |  | Piping
48 | KRS-P-MT-002 | MTO for Piping Manual Valve | 28 | 28 | 0.9712% | 1 | 2021-03-26 | 2020-12-22 |  |  | 2021-04-09 | 2021-01-28 |  | AWC | 2021-04-23 | 2021-03-15 |  |  | 2021-05-07 |  | 2021-03-31 | NA | Piping
F | INSTRUMENT |  | 752 | 736 | 25.53% | 22 | [16 empty] | Instrument
|  | Calculation | [20 empty] | Instrument
49 | KRS-I-CC-001 | Calculation for Control Valve | 32 | 100 | 3.469% | 1 | 2021-04-22 | 2020-12-30 |  |  | 2021-05-06 | 2021-01-27 |  | AWC | 2021-05-20 | 2021-03-29 |  |  | 2021-05-21 |  | 2021-04-08 | NA | Instrument
50 | KRS-I-CC-002 | Calculation for Restriction Orifice Plate | 32 | 24 | 0.8325% | 1 | 2021-04-12 | 2021-04-01 |  |  | 2021-04-26 | 2021-04-14 |  | AWC | 2021-05-10 | 2021-05-11 |  |  | 2021-05-21 |  |  |  | Instrument
|  | Datasheet | [20 empty] | Instrument
51 | KRS-I-DS-001 | Datasheet for PLC/DCS Safety Instrument System Temperature Indicator | 32 | 16 | 0.555% | 1 | 2021-03-23 | 2021-03-05 |  |  | 2021-04-06 | 2021-04-10 |  | AWC | 2021-04-20 | 2021-04-20 |  |  | 2021-05-04 | 2021-05-11 |  | APP | Instrument
52 | KRS-I-DS-002 | Datasheet for PSV and BDV (if any) Pressure Safety Valve | 32 | 16 | 0.555% | 1 | 2021-04-12 | 2021-03-15 |  |  | 2021-04-26 |  | 2021-04-09 | NA | 2021-05-10 |  |  |  | 2021-05-21 |  |  |  | Instrument
53 | KRS-I-DS-003 | Datasheet for Pressure Gauge | 32 | 16 | 0.555% | 1 | 2021-03-24 | 2021-03-05 |  |  | 2021-04-07 | 2021-04-10 |  | AWC | 2021-04-21 | 2021-04-21 |  |  | 2021-05-05 |  |  | NA | Instrument
54 | KRS-I-DS-004 | Datasheet for Level and Pressure Transmitter/Switch/Controller | 32 | 16 | 0.555% | 1 | 2021-04-22 | 2021-03-10 |  |  | 2021-05-06 | 2021-04-21 |  | APP | 2021-05-20 | 2021-04-23 |  |  | 2021-05-21 |  |  |  | Instrument
55 | KRS-I-DS-005 | Datasheet for Level Gauge (if any) | 32 | 16 | 0.555% | 1 | 2021-03-24 | 2021-03-05 |  |  | 2021-04-07 | 2021-04-10 |  | AWC | 2021-04-21 | 2021-04-21 |  |  | 2021-05-05 |  |  | NA | Instrument
56 | KRS-I-DS-006 | Datasheet for RO (Restriction Orifice) | 32 | 16 | 0.555% | 1 | 2021-04-30 | 2021-04-01 |  |  | 2021-05-06 |  | 2021-04-14 | NA | 2021-05-20 |  |  |  | 2021-06-03 |  |  |  | Instrument
57 | KRS-I-DS-007 | Datasheet for Gas Flow Transmitter (Non-intrusive)/Ultrasonic Flowmeter | 32 | 16 | 0.555% | 1 | 2021-04-02 | 2021-03-16 |  |  | 2021-04-16 | 2021-04-21 |  | AWC | 2021-04-30 | 2021-04-23 |  |  | 2021-05-21 |  |  |  | Instrument
58 | KRS-I-DS-008 | Datasheet for Pressure Control & Regulator Valve | 32 | 16 | 0.555% | 1 | 2021-04-30 | 2021-03-29 |  |  | 2021-05-07 |  | 2021-04-08 | NA | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Instrument
| KRS-I-DS-009 | Datasheet for On-Off Valve |  |  |  |  | 2021-04-23 | 2021-03-15 |  |  |  |  | 2021-04-09 | NA | 2021-05-07 |  |  |  | 2021-05-21 |  |  |  | Instrument
|  | List | [20 empty] | Instrument
59 | KRS-I-IN-001 | Instrument Index | 32 | 16 | 0.555% | 1 | 2021-04-09 | 2021-03-15 |  |  | 2021-04-23 |  |  |  | 2021-05-07 |  |  |  | 2021-05-21 |  |  |  | Instrument
60 | KRS-I-LI-001 | I/O List | 32 | 16 | 0.555% | 1 | 2021-04-09 | 2021-03-10 |  |  | 2021-04-23 | 2021-03-12 |  | AWC | 2021-05-07 | 2021-04-23 |  |  | 2021-05-21 |  |  |  | Instrument
61 | KRS-I-SC-001 | Tubing/Cable Schedule | 40 | 16 | 0.555% | 1 | 2021-04-09 | 2021-03-15 |  |  | 2021-04-23 | 2021-04-09 |  | AWC | 2021-05-07 | 2021-04-23 |  |  | 2021-05-21 |  |  |  | Instrument
|  | Drawing | [20 empty] | Instrument
62 | KRS-I-BD-001 | Drawing for Instrument & Control Block Diagram (Updated) | 26 | 24 | 0.8325% | 1 | 2021-03-19 | 2020-12-16 |  | Re-IFR | 2021-04-02 | 2021-04-09 |  | AWC | 2021-04-16 | 2021-04-14 |  |  | 2021-04-30 |  |  |  | Instrument
63 | KRS-I-MC-001 | Drawing for Shutdown Hierarchy Diagram | 22 | 96 | 3.33% | 1 | 2021-05-07 | 2020-12-21 |  | Re-IFR | 2021-05-07 |  | 2021-01-08 | NA | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Instrument
64 | KRS-I-CE-001 | Cause and Effect Diagram | 48 | 96 | 3.33% | 1 | 2021-04-23 | 2020-12-30 |  |  | 2021-05-07 | 2021-01-27 |  | AWC | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Instrument
65 | KRS-I-IL-001 | Drawing for Instrument Location Plan (Updated) | 26 | 24 | 0.8325% | 1 | 2021-04-23 | 2021-03-15 |  |  | 2021-05-07 | 2021-04-09 |  | AWC | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Instrument
66 | KRS-I-IR-001 | Drawing for Instrument Tubing/Cable & Tray Routing (Updated) | 26 | 24 | 0.8325% | 1 | 2021-04-23 | 2021-03-15 |  |  | 2021-05-07 | 2021-04-28 |  | AWC | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Instrument
67 | KRS-I-IH-001 | Drawing for Instrument Hook-Up | 48 | 24 | 0.8325% | 1 | 2021-05-03 | 2021-03-08 |  |  | 2021-05-17 | 2021-03-18 |  | AWC | 2021-05-31 | 2021-04-23 |  |  | 2021-05-07 |  |  |  | Instrument
68 | KRS-I-MC-002 | Drawing for Instrument Installation Detail | 26 | 24 | 0.8325% | 1 | 2021-05-03 | 2021-03-15 |  |  | 2021-05-17 | 2021-04-10 |  | AWC | 2021-05-31 | 2021-04-23 |  |  | 2021-05-07 |  |  |  | Instrument
69 | KRS-I-WI-001 | Drawing for Wiring and Termination Diagram (Updated) | 56 | 94 | 3.26% | 1 | 2021-04-23 | 2020-12-18 |  |  | 2021-05-07 |  | 2021-01-22 | NA | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Instrument
|  | Material Take Off | [20 empty] | Instrument
70 | KRS-I-MT-001 | MTO for Instrument | 50 | 30 | 1.041% | 1 | 2021-04-23 | 2021-03-18 |  |  | 2021-05-07 |  | 2021-04-09 | NA | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Instrument
G | ELECTRICAL |  | 254 | 176 | 6.105% | 9 | [16 empty] | Electrical
|  | Calculation | [20 empty] | Electrical
71 | KRS-E-CC-001 | Cable Sizing Calculation | 26 | 32 | 1.11% | 1 | 2021-03-19 | 2021-02-11 |  |  | 2021-04-02 | 2021-03-10 |  | APP | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 |  |  |  | Electrical
72 | KRS-E-SC-001 | Cable Schedule | 22 | 32 | 1.11% | 1 | 2021-03-19 | 2021-02-11 |  |  | 2021-04-02 | 2021-03-10 |  | APP | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-06 | 243 | APP | Electrical
|  | Datasheet | [20 empty] | Electrical
73 | KRS-E-DS-001 | Datasheet for Electrical Motor (Deleted) | 30 | 16 | 0.555% | 1 | 2021-03-08 |  |  |  | 2021-03-22 |  |  |  | 2021-04-05 |  |  |  | 2021-04-19 | x |  |  | Electrical | ganti sistem jadi pompa pneumatik
|  | Drawing | [20 empty] | Electrical
74 | KRS-E-OD-001 | Drawing for Single Line Diagram | 56 | 16 | 0.555% | 1 | 2021-03-19 | 2021-03-08 |  |  | 2021-04-02 | 2021-03-12 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-03 | 231 | APP | Electrical
75 | KRS-E-LL-001 | Drawing for Lighting Layout | 24 | 16 | 0.555% | 1 | 2021-03-19 | 2021-03-08 |  |  | 2021-04-02 | 2021-03-12 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-03 | 231 | APP | Electrical
76 | KRS-E-GL-001 | Drawing for Grounding Layout | 24 | 16 | 0.555% | 1 | 2021-03-19 | 2021-03-08 |  |  | 2021-04-02 | 2021-03-12 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-03 | 231 | APP | Electrical
77 | KRS-E-ER-001 | Drawing for Cable Routing and Cable Tray Layout | 24 | 16 | 0.555% | 1 | 2021-03-19 | 2021-03-08 |  |  | 2021-04-02 | 2021-03-12 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-03 | 231 | APP | Electrical
78 | KRS-E-AC-001 | Drawing for Hazardous Area Classification | 24 | 16 | 0.555% | 1 | 2021-03-19 | 2021-03-08 |  |  | 2021-04-02 | 2021-03-12 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-03 | 231 | APP | Electrical
|  | Material Take Off | [20 empty] | Electrical
79 | KRS-E-MT-001 | MTO for Electrical | 24 | 16 | 0.555% | 1 | 2021-03-19 | 2021-03-08 |  |  | 2021-04-02 | 2021-03-18 |  | AWC | 2021-04-16 | 2021-04-07 |  |  | 2021-04-30 | 2021-05-03 |  | APP | Electrical
H | CIVIL |  | 246 | 227 | 7.874% | 9 | [16 empty] | Civil
|  | Study and Calculation | [20 empty] | Civil
80 | KRS-C-CC-001 | Calculation for Flare KO Drum Foundation and Shelter | 34 | 24 | 0.8325% | 1 | 2021-03-15 | 2020-12-28 |  |  | 2021-03-29 | 2021-01-20 |  | AWC | 2021-04-12 | 2021-03-29 |  |  | 2021-04-26 | 2021-03-31 |  | APP | Civil
81 | KRS-C-CC-002 | Calculation for Flare KO Drum Pump Foundation | 34 | 64 | 2.22% | 1 | 2021-03-19 | 2021-02-11 |  |  | 2021-04-02 | 2021-03-03 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-03 |  | APP | Civil
82 | KRS-C-CC-003 | Calculation for Flare Foundation | 34 | 16 | 0.555% | 1 | 2021-04-05 | 2021-02-02 |  |  | 2021-04-19 | 2021-02-15 |  | AWC | 2021-05-03 |  |  |  | 2021-05-17 |  |  |  | Civil
|  | Drawing | [20 empty] | Civil
83 | KRS-C-EF-001 | Drawing for Flare System Pipe Support Foundation | 24 | 64 | 2.22% | 1 | 2021-03-19 | 2020-12-28 |  |  | 2021-04-02 | 2021-01-20 |  | AWC | 2021-04-16 | 2021-04-01 |  |  | 2021-04-30 | 2021-05-06 | 242 | AWC | Civil
84 | KRS-C-MC-001 | Drawing for Flare KO Drum Foundation and Shelter | 24 | 8 | 0.2775% | 1 | 2021-03-19 | 2020-12-28 |  |  | 2021-04-02 | 2021-01-20 |  | AWC | 2021-04-16 | 2021-04-05 |  |  | 2021-04-30 | 2021-05-03 |  | AWC | Civil
85 | KRS-C-EF-002 | Drawing for Flare KO Drum Pump Foundation | 24 | 16 | 0.555% | 1 | 2021-03-19 | 2021-02-11 |  |  | 2021-04-02 | 2021-03-03 |  | AWC | 2021-04-16 | 2021-04-01 |  |  | 2021-04-30 | 2021-05-06 | 242 | APP | Civil
86 | KRS-C-EF-003 | Drawing for Flare Foundation | 24 | 16 | 0.555% | 1 | 2021-04-12 | 2021-02-08 |  |  | 2021-04-26 | 2021-02-15 |  | AWC | 2021-05-10 |  |  |  | 2021-05-24 |  |  |  | Civil
87 | KRS-C-MC-002 | Drawing for Pipe Trench at Flare Header | 24 | 3 | 0.1041% | 1 | 2021-04-12 | 2021-02-11 |  |  | 2021-04-26 | 2021-03-03 |  | AWC | 2021-05-10 |  |  |  | 2021-05-24 |  |  |  | Civil
|  | Material Take Off | [20 empty] | Civil
88 | KRS-C-MT-001 | MTO for Civil | 24 | 16 | 0.555% | 1 | 2021-04-12 | 2021-02-19 |  |  | 2021-04-26 | 2021-03-03 |  | AWC | 2021-05-10 |  |  |  | 2021-05-24 |  |  |  | Civil
|  | Total | 2883 | 2883 | 100% | 257
[23 empty] | S-Curve Data | S-Curve Data
2883
|  |  |  | 0 | [18 empty] | Plan | Plan
[23 empty] | Plan Cumm | Plan Cumm
Formulas:
Return = [Issued for Review (IFR)]+14
Return = [Issued for Approval (IFA)]+7
Issued for Review (IFR) = [Return]-14
Issued for Review (IFR) = [Issued for Approval (IFA)]-14
Issued for Approval (IFA) = [Return]-14
Note on I11: Zata Atsarina: Re-IFR 24 Mar'21
Note on Q11: Zata Atsarina: Re-submit 24 Mar 21 IFA 26 Mar 21
Note on I14: Zata Atsarina: Re-IFR on 29 Apr21
Note on I16: Zata Atsarina: ReIFR 29 Jan 21
Note on I17: Zata Atsarina: Re-IFR 1 Mar 21
Note on Q17: Zata Atsarina: Re-IFA 7 May'21
Note on U17: Zata Atsarina: Re-IFA App 7 May'21
Note on I19: Zata Atsarina: Re-IFR 8 Mar 21
Note on I20: Zata Atsarina: Re-IFR on 15 Feb 21
Note on M20: Zata Atsarina: Re-IFR
Note on Q20: Zata Atsarina: Replace on 27 Apr 21
Note on I26: Zata Atsarina: ReIFR 3 Feb 21
Note on Q26: Zata Atsarina: Re-IFA 7 May'21
Note on U26: Zata Atsarina: Re-IFA App 7 May'21
Note on I27: Zata Atsarina: ReIFR 3 Feb 21
Note on I29: Zata Atsarina: Re-IFR 3 Mar 21
Note on I31: Zata Atsarina: Re-IFR 3 Mar 21
Note on I33: Zata Atsarina: Re-IFR 3 Mar 21
Note on I39: Zata Atsarina: Re-IFR 3 Mar 21
Note on I42: Zata Atsarina: Re-IFR 3 Mar 21
Note on I45: Zata Atsarina: Re-IFR 3 Mar 21
Note on I46: Zata Atsarina: Re-IFR 3 Mar 21
Note on Q47: Zata Atsarina: Re-IFA 7 May'21
Note on U47: Zata Atsarina: ReIFA APP 7 May'21
Note on Q48: Zata Atsarina: Re-IFA 7 May'21
Note on U48: Zata Atsarina: ReIFA APP 7 May'21
Note on Q49: Zata Atsarina: Re-IFA 7 May'21
Note on U49: Zata Atsarina: ReIFA APP 7 May'21
Note on I52: Zata Atsarina: ReIFR 5 Feb 21 Re-IFR 19 Feb 21
Note on Q57: Zata Atsarina: Re-IFA 7 May'21
Note on I58: Zata Atsarina: Re-IFR on 15 Mar 21
Note on Q59: Zata Atsarina: Re-IFA on 11 May'21
Note on I62: Zata Atsarina: Re-IFR on 15 Mar 21
Note on I63: Zata Atsarina: Re-IFR 15 Mar 21
Note on I67: Zata Atsarina: Re-IFR on 15 Mar 21
Note on Q67: Zata Atsarina: diclaim bareng sama piping GA, salah
Note on I68: Zata Atsarina: Re-IFR 22 Mar 21
Note on N68: Zata Atsarina: NA Re-IFR on 22 Apr21
Note on I71: Zata Atsarina: Re-IFR 29 Mar 21
Note on M71: Zata Atsarina: IFR NA 15 Feb 21
Note on Q72: Zata Atsarina: Re-IFA on 23 Apr'21
Note on I79: Zata Atsarina: Re-IFR 20 Apr'21
Note on I81: Zata Atsarina: Re-IFR 16 Mar 21
Note on B86: Zata Atsarina: New
Note on I86: Zata Atsarina: Re-IFR on 14 Apr21
Note on I92: Zata Atsarina: Re-IFR on 15 mar 21
Note on Q92: Zata Atsarina: Re-IFA on 17 May'21
Note on I93: Zata Atsarina: Re-IFR 9 APr21
Note on N93: Zata Atsarina: Re-IFR 27 Apr21 NA
Note on I99: Zata Atsarina: Re-IFR on 14 Apr21
Note on Q109: Zata Atsarina: Replace on 3 May'21
Note on Q110: Zata Atsarina: Replace on 3 May'21
Note on Q111: Zata Atsarina: Replace on 3 May'21
Note on Q112: Zata Atsarina: Replace on 3 May'21
Note on Q113: Zata Atsarina: Replace on 3 May'21
Note on I119: Zata Atsarina: progress di-claim tgl 28 Dec 20