## MDR
PROJECT 3
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
No |  |  | MH CTR | MH yg Dikirim | MH Distribusi | MH Hasil Hitungan | Weight Factor | DOC.QTY | Issued for Review (IFR) | [7 empty] | Issued for Approval (IFA) | [7 empty] | Discipline | Remark
| Doc.Number | Document Title
[9 empty] | Submit |  |  |  | Return |  |  |  | Submit |  |  |  | Return
[9 empty] | New Plan | Actual | Transmittal | Status | New Plan | Actual | Transmittal | Status | New Plan | Actual Date | Transmittal | Status | New Plan | Actual | Transmittal | Status
A | SITE VISIT |  | 170 | 170 | 911 | 404 | 15.04% | 1 | [16 empty] | General
|  | Site Visit | [22 empty] | General
1 | activity | Site Visit Verification | 128 | 128 | 869 | 320 | 11.91% |  | 2020-12-21 | 2020-12-21 | x | started | 2020-12-24 | x | x | x | 2020-12-27 | 2020-12-30 | x | finished | 2020-12-30 | 2020-12-30 | x | finished | General
|  | Site Visit Report | [22 empty] | General
2 | SMK-G-RE-001 | Site Visit Report | 42 | 42 | 42 | 84 | 3.126% | 1 | 2021-03-22 | 2020-12-31 | 011 |  | 2021-04-16 | 2021-01-15 | 027 | - | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | General
B | GENERAL |  | 0 | 8 | 8 | 38 | 1.414% | 4 | [16 empty] | PMT
|  | PROJECT MANAGEMENT | [22 empty] | PMT
3 | SMK-G-WR-X | Weekly Report | 0 | 8 | 8 | 12 | 0.4466% | 1 | 2020-12-31 | 2020-12-31 | 013 |  | 2020-12-31 |  |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | PMT
3 | SMK-G-MDR-001 | Master Deliverable Register |  |  |  | 10 | 0.3722% | 1 | 2020-12-31 | 2020-12-31 | 012 |  | 2020-12-31 |  |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | PMT
3 | SMK-G-SC-001 | Overall Schedule |  |  |  | 8 | 0.2977% | 1 | 2020-12-31 | 2020-12-31 | 012 |  | 2020-12-31 | ` |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | PMT
3 | SMK-G-SC-002 | S-Curve |  |  |  | 8 | 0.2977% | 1 | 2020-12-31 | 2020-12-31 | 012 |  | 2020-12-31 |  |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | PMT
C | PROCESS |  | 1069 | 1327 | 338 | 840 | 31.26% | 48 | [16 empty] | Process
|  | Design Basis and Philosophy | [22 empty] | Process
4 | SMK-R-DB-001 | Project Design Basis | 22 | 22 | 11 | 120 | 4.466% | 1 | 2020-12-31 | 2020-12-31 | 012 |  | 2021-01-14 | TBA | TBA | NA | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Process | to Re-IFR
|  | Study and Calculation | [22 empty] | Process
5 | SMK-R-CC-001 | Process Simulation Report | 58 | 40 | 20 | 28 | 1.042% | 1 | 2021-03-17 | 2020-12-31 | 011 |  | 2021-01-27 | 2021-01-27 | 052 | NA | 2021-04-12 | 2021-04-12 | 031 |  | 2021-04-30 | 2021-05-03 | 230 | APP | Process
6 | SMK-R-CC-002 | Vessel and Separator Sizing and Study Report (directly to IFA) | 20 | 40 | 20 | 40 | 1.489% | 1 | 2021-03-01 | 2020-12-31 | 012 |  | 2021-01-21 | 2021-01-21 | 022 | NA | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Process
7 | SMK-R-SY-001 | Flare System Line Study | 54 | 54 | 27 | 54 | 2.01% | 1 | 2020-12-31 | 2020-12-31 | 012 |  | 2021-01-26 | 2021-01-26 | 049 | NA | 2021-01-14 |  |  |  | 2021-01-28 |  |  |  | Process | to Re-IFR
8 | SMK-R-SY-002 | Relief and Blowdown Study Report | 84 | 68 | 34 | 68 | 2.531% | 1 | 2020-12-31 | 2020-12-31 | 012 |  | 2021-01-28 | 2021-01-28 | 061 | NA | 2021-01-14 |  |  |  | 2021-01-28 |  |  |  | Process | to Re-IFR
9 | SMK-R-CC-003 | Calculation for Flare KO Drum Pump Sizing | 26 | 40 | 20 | 40 | 1.489% | 1 | 2021-03-17 | 2020-12-31 | 012 |  | 2021-01-21 | 2021-01-21 | TBA | NA | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Process
10 | SMK-R-SY-003 | Utility (IA, Fuel Gas, Purge Gas) Consumption Study | 40 | 40 | 20 | 11 | 0.4094% | 1 | 2021-03-22 | 2021-03-22 | 028 |  | 2021-03-26 | 2021-03-26 | 164 | NA | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Process | to Re-IFR
|  | List | [22 empty] | Process
11 | SMK-R-LI-001 | Line List | 22 | 22 | 11 | 11 | 0.4094% | 1 | 2021-04-30 |  |  |  | 2021-05-21 |  |  |  | 2021-06-14 |  |  |  | 2021-06-28 |  |  |  | Process
12 | SMK-R-TI-002 | Tie-In Point List | 22 | 22 | 11 | 11 | 0.4094% | 1 | 2021-04-30 |  |  |  | 2021-05-21 |  |  |  | 2021-06-14 |  |  |  | 2021-06-28 |  |  |  | Process
|  | Drawing | [22 empty] | Process
13 | SMK-R-PF-001 | PFD Semangka Gas Station (directly to IFA) | 11 | 25 | 12.5 | 25 | 0.9304% | 1 | 2021-03-22 | 2020-12-31 | 011 |  | 2021-03-30 | 2021-01-27 | 052 | NA | 2021-04-20 | 2021-04-20 | 033 |  | 2021-05-04 |  |  |  | Process | to IFA
14 | SMK-R-HMB-001 | Heat and Material Balance | 58 | 29 | 14 | 25 | 0.9304% | 1 | 2021-03-22 | 2020-12-31 | 011 |  | 2021-03-30 | 2021-01-27 | 052 | NA | 2021-04-12 | 2021-04-12 | 031 |  | 2021-04-30 | 2021-05-03 | 230 | APP | Process
15 | SMK-R-PI-001 | P&ID Test or Production Manifold | 28 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
16 | SMK-R-PI-001_D | P&ID Test or Production Manifold (Demolition) | 28 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
17 | SMK-R-PI-004 | P&ID Pig Launcher & Pig Receiver | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
18 | SMK-R-PI-004_D | P&ID Pig Launcher & Pig Receiver (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
19 | SMK-R-PI-006 | P&ID LP Production Separator | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
20 | SMK-R-PI-006_D | P&ID LP Production Separator (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
21 | SMK-R-PI-007 | P&ID Slug Catcher | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
22 | SMK-R-PI-007_D | P&ID Slug Catcher (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
23 | SMK-R-PI-008 | P&ID Piping System | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
24 | SMK-R-PI-008_D | P&ID Piping System (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
25 | SMK-R-PI-009 | P&ID LP Suction Scrubber | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
26 | SMK-R-PI-009_D | P&ID LP Suction Scrubber (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
27 | SMK-R-PI-011 | P&ID MP Suction Scrubber | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
28 | SMK-R-PI-011_D | P&ID MP Suction Scrubber (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
29 | SMK-R-PI-013 | P&ID HP Discharge Scrubber | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
30 | SMK-R-PI-013_D | P&ID HP Discharge Scrubber (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
31 | SMK-R-PI-015 | P&ID Flaring System, Flare KO Drum and Pump, Flare Stack | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
32 | SMK-R-PI-015_D | P&ID Flaring System (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
33 | SMK-R-PI-016 | P&ID Fuel Gas Scrubber | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
34 | SMK-R-PI-016_D | P&ID Fuel Gas Scrubber (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
35 | SMK-R-PI-017 | P&ID Liquid Line Header | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
36 | SMK-R-PI-017_D | P&ID Liquid Line Header (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
37 | SMK-R-PI-018 | P&ID Line Header MP Compressor | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
38 | SMK-R-PI-018_D | P&ID Line Header MP Compressor (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
39 | SMK-R-PI-022 | P&ID Fire Water System | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
40 | SMK-R-PI-022_D | P&ID Fire Water System (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
41 | SMK-R-PI-023 | P&ID Instrument Air System | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
42 | SMK-R-PI-023_D | P&ID Instrument Air System (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
43 | SMK-R-PI-025 | P&ID Header LP Compressor | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
44 | SMK-R-PI-025_D | P&ID Header LP Compressor (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
45 | SMK-R-PI-030 | P&ID Glycol Contractor MAFT-111 | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
46 | SMK-R-PI-030_D | P&ID Glycol Contractor MAFT-111 (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
47 | SMK-R-PI-034 | P&ID Gas Metering SMK-ZAU-105 | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
48 | SMK-R-PI-034_D | P&ID Gas Metering SMK-ZAU-105 (Demolition) | 16 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-16 | 2021-04-16 | 032 |  | 2021-04-30 | 2021-05-06 | 246 | AWC | 2021-05-31 |  |  |  | 2021-06-14 |  |  |  | Process
49 | SMK-R-UF-001 | UHD for Fuel Gas Distribution | 28 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-30 | 2021-05-07 | 044 |  | 2021-05-21 |  |  |  | 2021-06-07 |  |  |  | 2021-06-21 |  |  |  | Process | to IFR
50 | SMK-R-UF-002 | UHD for IA/UA Distribution | 28 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-30 | 2021-05-07 | 044 |  | 2021-05-21 |  |  |  | 2021-06-07 |  |  |  | 2021-06-21 |  |  |  | Process | to IFR
51 | SMK-R-UF-003 | UHD for Flare and Vent Distribution | 28 | 25 | 12.5 | 11 | 0.4094% | 1 | 2021-04-30 | 2021-05-07 | 044 |  | 2021-05-21 |  |  |  | 2021-06-07 |  |  |  | 2021-06-21 |  |  |  | Process | to IFR
D | PROCESS SAFETY |  | 188 | 188 | 311 | 102 | 3.796% | 3 | [16 empty] | ProSaf
|  | Study and Calculation | [22 empty] | ProSaf
52 | SMK-F-SY-001 | Study for Flare Radiation and Dispersion | 62 | 62 | 248 | 80 | 2.977% | 1 | 2021-03-18 | 2020-12-18 | 003 |  | 2021-03-30 | 2021-01-08 | 009 | NA | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | ProSaf | to IFA
53 | SMK-F-CC-001 | Calculation for Fire Water Demand | 90 | 90 | 45 | 11 | 0.4094% | 1 | 2021-01-26 | 2021-01-26 | 015 |  | 2021-03-15 | 2021-03-15 | TBA | AWC | 2021-03-31 | 2021-03-31 | 30 |  | 2021-04-30 | 2021-05-03 | 230 | APP | ProSaf
54 | SMK-F-RE-001 | HAZOP and HAZID Close-Out Report | 36 | 36 | 18 | 11 | 0.4094% | 1 | TBA |  |  |  | TBA |  |  |  | TBA |  |  |  | 2021-07-02 |  |  |  | ProSaf
E | MECHANICAL |  | 72 | 72 | 36 | 144 | 5.359% | 3 | [16 empty] | Mechanical
|  | Datasheet | [22 empty] | Mechanical
55 | SMK-M-DS-001 | Datasheet for Flare KO Drum | 16 | 16 | 8 | 32 | 1.191% | 1 | 2020-12-31 | 2020-12-31 | 011 |  | 2021-01-18 | 2021-01-18 | 027 | AWC | 2021-03-29 | 2021-03-29 | 029 |  | 2021-03-31 | 2021-03-31 | 171 | AWC | Mechanical
56 | SMK-M-DS-002 | Datasheet for Flare KO Drum Pump and Pit Sum Pump and Pit Sum Pump | 16 | 16 | 8 | 32 | 1.191% | 1 | 2021-03-29 | 2020-12-31 | 011 |  | 2021-03-31 | 2021-01-18 | 027 | NA | 2021-04-27 |  |  |  | 2021-05-18 |  |  |  | Mechanical | to IFA
57 | SMK-M-DS-003 | Datasheet for Flare Tip and Ignition System Package | 40 | 40 | 20 | 80 | 2.977% | 1 | 2020-12-31 | 2020-12-31 | 011 |  | 2021-01-28 | 2021-01-28 | 061 | AWC | 2021-04-27 |  |  |  | 2021-05-18 |  |  |  | Mechanical | to IFA
F | PIPING |  | 308 | 300 | 150 | 566 | 21.06% | 8 | [16 empty] | Piping
|  | Datasheet | [22 empty] | Piping
58 | SMK-P-DS-001 | Datasheet for Manual Valve | 28 | 28 | 14 | 56 | 2.084% | 1 | 2020-12-29 | 2020-12-29 | 009 |  | 2021-01-28 | 2021-01-28 | 061 | NA | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Piping | to Re-IFR
59 | SMK-P-DS-002 | Datasheet and List of Piping Specialty Item | 28 | 28 | 14 | 56 | 2.084% | 1 | 2020-12-30 | 2020-12-30 | 010 |  | 2021-01-26 | 2021-01-26 | 049 | AWC | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Piping | to IFA
|  | Drawing | [22 empty] | Piping
60 | SMK-P-PL-001 | Plot Plan Equipment Layout | 8 | 30 | 15 | 60 | 2.233% | 1 | 2020-12-18 | 2020-12-18 | 004 |  | 2021-01-26 | 2021-01-26 | 049 | AWC | 2021-04-23 |  |  |  | 2021-05-07 |  |  |  | Piping | to IFA
61 | SMK-P-GA-002 | Piping General Arrangement Layout for Flare System | 86 | 56 | 28 | 103 | 3.833% | 1 | 2020-12-29 | 2020-12-29 | 009 |  | 2021-01-28 | 2021-01-28 | 061 | NA | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Piping | to Re-IFR
62 | SMK-P-IS-001 | Isometric Drawing for Flare System | 86 | 56 | 28 | 103 | 3.833% | 1 | 2020-12-31 | 2020-12-31 | 011 |  | 2021-01-28 | 2021-01-28 | 061 | NA | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Piping | to Re-IFR
63 | SMK-P-PS-001 | Pipe Support Drawing for Flare System | 0 | 30 | 15 | 60 | 2.233% | 1 | 2020-12-18 | 2020-12-18 | 002 |  | 2021-01-26 | 2021-01-26 | 049 | AWC | 2021-04-30 |  |  |  | 2021-05-21 |  |  |  | Piping | to IFA
|  | Drawing | [22 empty] | Piping
64 | SMK-P-MT-001 | MTO for Piping Bulk | 40 | 40 | 20 | 64 | 2.382% | 1 | 2020-12-31 | 2020-12-31 | 011 |  | 2021-01-28 | 2021-01-28 | 061 | NA | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Piping | to Re-IFR
65 | SMK-P-MT-002 | MTO for Piping Manual Valve | 32 | 32 | 16 | 64 | 2.382% | 1 | 2020-12-22 | 2020-12-22 | 005 |  | 2021-01-27 | 2021-01-27 | 052 | AWC | 2021-04-23 |  |  |  | 2021-05-07 |  |  |  | Piping | to IFA
G | INSTRUMENT |  | 672 | 672 | 490 | 407 | 15.15% | 24 | [16 empty] | Instrument
|  | Calculation | [22 empty] | Instrument
66 | SMK-I-CC-001 | Calculation for Control Valve | 32 | 32 | 16 | 11 | 0.4094% | 1 | 2021-05-28 |  |  |  | 2021-06-11 |  |  |  | 2021-07-02 |  |  |  | 2021-07-09 |  |  |  | Instrument
67 | SMK-I-CC-002 | Calculation for Restriction Orifice Plate | 32 | 32 | 16 | 11 | 0.4094% | 1 | 2021-05-28 |  |  |  | 2021-06-11 |  |  |  | 2021-07-02 |  |  |  | 2021-07-09 |  |  |  | Instrument
|  | Datasheet | [22 empty] | Instrument
68 | SMK-I-DS-001 | Datasheet for PLC/DCS Safety Instrument System (Deleted) | 24 | 24 | 12 | 11 | 0.4094% | 1 | 2021-03-11 | x |  |  | 2021-03-25 | x |  |  | 2021-04-08 | x |  |  | 2021-04-22 | x |  |  | Instrument
69 | SMK-I-DS-002 | Datasheet for PSV and BDV (if any) On-off Valve | 24 | 24 | 12 | 11 | 0.4094% | 1 | 2021-04-21 | 2021-04-21 | 034 |  | 2021-05-05 |  |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Instrument
70 | SMK-I-DS-003 | Datasheet for Pressure Gauge | 24 | 24 | 12 | 11 | 0.4094% | 1 | 2021-04-20 | 2021-04-20 | 033 |  | 2021-05-04 |  |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Instrument
71 | SMK-I-DS-004 | Datasheet for Level and Pressure Transmitter/Switch/Controller | 24 | 24 | 12 | 11 | 0.4094% | 1 | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | 2021-06-18 |  |  |  | 2021-06-25 |  |  |  | Instrument
72 | SMK-I-DS-005 | Datasheet for Level Gauge (if any) | 24 | 24 | 12 | 11 | 0.4094% | 1 | 2021-04-20 | 2021-04-20 | 033 |  | 2021-05-04 |  |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Instrument
73 | SMK-I-DS-006 | Datasheet for RO (Restriction Orifice) | 24 | 24 | 12 | 11 | 0.4094% | 1 | 2021-05-28 |  |  |  | 2021-06-11 |  |  |  | 2021-07-02 |  |  |  | 2021-07-09 |  |  |  | Instrument
74 | SMK-I-DS-007 | Datasheet for Gas Flow Transmitter (Non-intrusive)/Ultrasonic Flowmeter | 24 | 24 | 12 | 11 | 0.4094% | 1 | 2021-05-28 |  |  |  | 2021-06-11 |  |  |  | 2021-07-02 |  |  |  | 2021-07-09 |  |  |  | Instrument
75 | SMK-I-DS-008 | Datasheet for Pressure Control & Regulator Valve | 24 | 24 | 12 | 11 | 0.4094% | 1 | 2021-05-28 |  |  |  | 2021-06-11 |  |  |  | 2021-07-02 |  |  |  | 2021-07-09 |  |  |  | Instrument
76 | SMK-I-DS-009 | Datasheet for BDV (Blowdown Valve) | 32 | 32 | 16 | 11 | 0.4094% | 1 | 2021-04-20 | 2021-04-20 | 033 |  | 2021-05-04 |  |  |  | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Instrument
77 | SMK-I-DS-010 | Datasheet for SDV (Shutdown Valve) | 32 | 32 | 16 | 11 | 0.4094% | 1 | 2021-04-21 | 2021-04-21 | 034 |  | 2021-05-05 |  |  |  | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Instrument
|  | List | [22 empty] | Instrument
78 | SMK-I-IN-001 | Instrument Index | 32 | 32 | 16 | 11 | 0.4094% | 1 | 2021-04-20 | 2021-04-20 | 033 |  | 2021-05-04 |  |  |  | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Instrument
79 | SMK-I-LI-001 | I/O List | 32 | 32 | 16 | 11 | 0.4094% | 1 | 2021-04-20 | 2021-04-20 | 033 |  | 2021-05-04 |  |  |  | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Instrument
80 | SMK-I-SC-001 | Tubing/Cable Schedule | 40 | 40 | 20 | 11 | 0.4094% | 1 | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Instrument
|  | Drawing | [22 empty] | Instrument
81 | SMK-I-CA-001 | Architecture Diagram Drawing for Instrument & Control Block Diagram (Updated) | 26 | 26 | 104 | 52 | 1.935% | 1 | 2020-12-14 | 2020-12-14 | 001 |  | 2021-01-22 | 2021-01-22 | 041 | NA | 2020-12-28 |  |  |  | 2021-01-04 |  |  |  | Instrument | to Re-IFR
82 | SMK-I-MC-001 | Drawing for Shutdown Hierarchy Diagram | 18 | 18 | 72 | 36 | 1.34% | 1 | 2020-12-14 | 2020-12-14 | 001 |  | 2021-01-22 | 2021-01-22 | 041 | NA | 2020-12-28 |  |  |  | 2021-01-04 |  |  |  | Instrument | to Re-IFR
83 | SMK-I-CE-001 | Cause and Effect Diagram | 46 | 46 | 23 | 52 | 1.935% | 1 | 2020-12-29 | 2020-12-29 | 008 |  | 2021-01-27 | 2021-01-27 | 056 | AWC | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Instrument | to IFA
84 | SMK-I-IL-001 | Drawing for Instrument Location Plan (Updated) | 26 | 26 | 13 | 11 | 0.4094% | 1 | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | 2021-07-02 |  |  |  | 2021-07-09 |  |  |  | Instrument
85 | SMK-I-IR-001 | Drawing for Instrument Tubing/Cable & Tray Routing (Updated) | 26 | 26 | 13 | 11 | 0.4094% | 1 | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | 2021-07-02 |  |  |  | 2021-07-09 |  |  |  | Instrument
86 | SMK-I-IH-001 | Drawing for Instrument Hook-Up | 0 | 13 | 6.5 | 4 | 0.1489% | 1 | 2021-04-22 | 2021-04-22 | 035 |  | 2021-05-06 |  |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Instrument
87 | SMK-I-MC-002 | Drawing for Instrument Installation Detail | 0 | 13 | 6.5 | 4 | 0.1489% | 1 | 2021-04-22 | 2021-04-22 | 035 |  | 2021-05-06 |  |  |  | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Instrument
88 | SMK-I-WI-001 | Drawing for Wiring and Termination Diagram (Updated) | 56 | 30 | 15 | 60 | 2.233% | 1 | 2020-12-23 | 2020-12-23 | 008 |  | 2021-01-07 | 2021-01-07 | 006 | NA | 2021-01-06 |  |  |  | 2021-01-13 |  |  |  | Instrument | to Re-IFR
|  | Material Take Off | [22 empty] | Instrument
89 | SMK-I-MT-001 | MTO for Instrument | 50 | 50 | 25 | 12 | 0.4466% | 1 | 2021-05-28 |  |  |  | 2021-06-11 |  |  |  | 2021-07-02 |  |  |  | 2021-07-09 |  |  |  | Instrument
I | ELECTRICAL |  | 216 | 216 | 108 | 90 | 3.349% | 9 | [16 empty] | Electrical
|  | Calculation | [22 empty] | Electrical
90 | SMK-E-CC-001 | Cable Sizing Calculation | 20 | 20 | 10 | 10 | 0.3722% | 1 | 2021-03-29 | 2021-03-29 | 029 |  | 2021-04-30 | 2021-04-27 | 215 | AWC | 2021-05-21 | 2021-05-21 | 048 | IFA | 2021-06-04 |  |  |  | Electrical
91 | SMK-E-SC-001 | Cable Schedule | 22 | 22 | 11 | 10 | 0.3722% | 1 | 2021-03-29 | 2021-03-29 | 029 |  | 2021-04-30 | 2021-04-27 | 215 | AWC | 2021-05-21 | 2021-05-21 | 048 | IFA | 2021-06-04 |  |  |  | Electrical
|  | Datasheet | [22 empty] | Electrical
92 | SMK-E-DS-001 | Datasheet for Electrical Motor (Deleted) | 22 | 22 | 11 | 10 | 0.3722% | 1 | TBA |  |  |  | TBA |  |  |  | TBA |  |  |  | 2021-04-22 | x |  |  | Electrical
|  | Drawing | [22 empty] | Electrical
93 | SMK-E-OD-001 | Drawing for Single Line Diagram | 56 | 32 | 16 | 10 | 0.3722% | 1 | 2021-03-29 | 2021-03-29 | 029 |  | 2021-04-30 | 2021-04-27 | 215 | AWC | 2021-05-28 | 2021-05-31 |  | IFA | 2021-06-11 |  |  |  | Electrical
94 | SMK-E-LL-001 | Drawing for Lighting Layout | 24 | 24 | 12 | 10 | 0.3722% | 1 | 2021-03-29 | 2021-03-29 | 029 |  | 2021-04-30 | 2021-04-27 | 215 | AWC | 2021-05-28 | 2021-05-31 |  | IFA | 2021-06-11 |  |  |  | Electrical
95 | SMK-E-GL-001 | Drawing for Grounding Layout | 24 | 24 | 12 | 10 | 0.3722% | 1 | 2021-03-29 | 2021-03-29 | 029 |  | 2021-04-30 | 2021-04-27 | 215 | AWC | 2021-05-28 | 2021-05-31 |  | IFA | 2021-06-11 |  |  |  | Electrical
96 | SMK-E-ER-001 | Drawing for Cable Routing and Cable Tray Layout | 24 | 24 | 12 | 10 | 0.3722% | 1 | 2021-03-29 | 2021-03-29 | 029 |  | 2021-04-30 | 2021-04-27 | 215 | AWC | 2021-05-28 | 2021-05-31 |  | IFA | 2021-06-11 |  |  |  | Electrical
97 | SMK-E-AC-001 | Area Classification Layout Drawing for Hazardous Area Classification | 0 | 24 | 12 | 10 | 0.3722% | 1 | 2021-03-29 | 2021-03-29 | 029 |  | 2021-04-30 | 2021-04-27 | 215 | AWC | 2021-05-28 | 2021-05-31 |  | IFA | 2021-06-11 |  |  |  | Electrical
|  | Material Take Off | [22 empty] | Electrical
98 | SMK-E-MT-001 | MTO for Electrical | 24 | 24 | 12 | 10 | 0.3722% | 1 | 2020-12-31 | 2020-12-31 | 30 |  | 2021-04-30 | 2021-04-27 | 215 | AWC | 2021-06-04 |  |  |  | 2021-06-18 |  |  |  | Electrical
J | CIVIL |  | 98 | 98 | 49 | 96 | 3.573% | 9 | [16 empty] | Civil
|  | Study and Calculation | [22 empty] | Civil
99 | SMK-C-CC-001 | Calculation for Flare KO Drum Foundation and Shelter | 24 | 12 | 6 | 24 | 0.8932% | 1 | 2020-12-28 | 2020-12-28 | 007 |  | 2021-01-20 | 2021-01-20 | 035 | AWC | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Civil | to IFA
100 | SMK-C-CC-002 | Calculation for Flare KO Drum Pump Foundation | 24 | 12 | 6 | 4 | 0.1489% | 1 | 2021-02-11 | 2021-02-11 | 019 |  | 2021-03-03 | 2021-03-03 | 100 | AWC | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Civil | to IFA
101 | SMK-C-CC-003 | Calculation for Flare Foundation | 24 | 12 | 6 | 4 | 0.1489% | 1 | 2021-02-02 | 2021-02-02 | 016 |  | 2021-02-15 | 2021-02-15 | 080 | AWC | 2021-05-21 |  |  |  | 2021-06-04 |  |  |  | Civil | to IFA
|  | Remaining Life Assessment | [22 empty] | Civil
102 | SMK-C-EF-001 | Drawing for Flare System Pipe Support Foundation | 0 | 8 | 4 | 24 | 0.8932% | 1 | 2020-12-28 | 2020-12-28 | 007 |  | 2021-01-20 | 2021-01-20 | 035 | AWC | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Civil | to IFA
103 | SMK-C-MC-001 | Drawing for Flare KO Drum Foundation and Shelter | 0 | 8 | 4 | 24 | 0.8932% | 1 | 2020-12-28 | 2020-12-28 | 007 |  | 2021-01-20 | 2021-01-20 | 035 | AWC | 2021-06-04 |  |  |  | 2021-06-18 |  |  |  | Civil | to IFA
104 | SMK-C-EF-002 | Drawing for Flare KO Drum Pump Foundation | 0 | 8 | 4 | 4 | 0.1489% | 1 | 2021-02-11 | 2021-02-11 | 018 |  | 2021-03-03 | 2021-03-03 | 100 | AWC | 2021-06-04 |  |  |  | 2021-06-18 |  |  |  | Civil | to IFA
105 | SMK-C-EF-003 | Drawing for Flare Foundation | 0 | 8 | 4 | 4 | 0.1489% | 1 | 2021-02-08 | 2021-02-08 | 017 |  | 2021-02-15 | 2021-02-15 | 080 | AWC | 2021-06-11 |  |  |  | 2021-06-25 |  |  |  | Civil | to IFA
106 | SMK-C-MC-002 | Drawing for Pipe Trench at Flare Header | 0 | 8 | 4 | 4 | 0.1489% | 1 | 2021-02-26 | 2021-02-26 | 021 |  | 2021-03-05 | 2021-03-05 | 104 | AWC | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Civil | to IFA
|  | Material Take Off | [22 empty] | Civil
107 | SMK-C-MT-001 | MTO for Civil | 26 | 22 | 11 | 4 | 0.1489% | 1 | 2021-02-26 | 2021-02-26 | 021 |  | 2021-03-05 | 2021-03-05 | 104 | AWC | 2021-06-18 |  |  |  | 2021-07-02 |  |  |  | Civil | to IFA
|  | Total | 2793 | 3051 | 2401 | 2687 | 100% | 106
-364
Formulas:
Return = [Issued for Approval (IFA)]+14
Return = [Issued for Review (IFR)]+14
Issued for Approval (IFA) = [Issued for Review (IFR)]+14
Issued for Approval (IFA) = [Return]-14
Issued for Review (IFR) = [Return]-14
Note on N34: Achmad el Fayed: First Re-IFR review 9 Mar 21 TRM 114
Note on N35: Achmad el Fayed: First Re-IFR review 9 Mar 21 TRM 114
Note on J75: Achmad el Fayed: First Re-IFR 17 Feb 21 TRM 020
Note on N75: Achmad el Fayed: First Re-IFR review 9 Mar 21 TRM 114
Note on B89: Achmad el Fayed: dulunya RBT-P-PP-002