## MDR
MASTER DOCUMENT REGISTER
PROJECT 4
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
No. | Doc. Numbering | Deliverables | Dur IFR | Weight Factor | Start |  | Draft |  | Issued for Review (IFR) | [5 empty] | Issued for Approval (IFA) | [5 empty] | Re-IFA |  | Approved for Construction (AFC) |  |  |  | Discipline | Remarks
[5 empty] | 10% |  | 30%
[5 empty] | Plan | Actual | Plan | Actual | Plan | Old Plan | Trm. | Actual | Trm. | Return | Plan | Old Plan | Trm. | Actual | Trm. | Return | Trm. | Actual | Plan | Old Plan | Trm. | Actual
PROJECT 4
1 | GENERAL DOCUMENT | [25 empty] | General
1.1 | BK06-BRU-9Q-00-001 | Cost Estimation | 7 days | 1.4% |  |  |  | 2020-10-09 | 2020-09-11 | 2020-09-11 | 594 | 2020-12-30 |  |  | 2020-09-25 | 2020-09-25 | [6 empty] | 2020-10-15 | 2020-10-02 |  |  | General | waiting for IFR Review
2 | PROCESS | [25 empty] | Process
2.1 | BK06-BRU-0J-00-001 | Separator Sizing | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-07-02 | 2020-07-02 | 404 | 2020-07-10 | wil | 2020-07-15 | 2020-07-16 | 2020-07-16 | 478 | 2020-08-24 | wil | 2020-08-31 | x | x | 2020-10-08 | 2020-09-09 | rep | 2020-11-26 | Process | Approved
2.2 | BK06-BRU-0J-00-002 | Tank Sizing | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-07-02 | 2020-07-02 | 404 | 2020-07-10 | wil | 2020-07-15 | 2020-07-16 | 2020-07-16 | 478 | 2020-08-24 | wil | 2020-08-31 | x | x | 2020-10-08 | 2020-09-09 | rep | 2020-11-26 | Process | Approved
2.3 | BK06-BRU-0J-00-003 | Line Sizing | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-07-02 | 2020-07-02 | 404 | 2020-07-10 | wil | 2020-07-15 | 2020-07-16 | 2020-07-16 | 478 | 2020-08-24 | wil | 2020-08-27 | x | x | 2020-10-08 | 2020-09-09 | rep | 2020-11-26 | Process | Approved
2.4 | BK06-BRU-0J-00-004 | PSV & Control Valve Sizing | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-07-09 | 2020-07-09 | 404 | 2020-07-10 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 512 | 2020-09-22 | x | x | x | x | 2020-10-08 | 2020-09-09 | rep | 2020-11-26 | Process | Approved
2.5 | BK06-BRU-0J-00-005 | Utility Demand and Sizing for Pigging Facility | 5 days | 0.8% |  | 2020-07-03 |  | 2020-07-10 | 2020-07-09 | 2020-07-09 | 512 | 2020-09-22 | wil | 2020-10-22 | 2020-07-23 | 2020-07-23 | 558 | 2020-11-05 | wil | 2020-11-16 | x | x | 2020-10-08 | 2020-09-09 | 577 | 2020-11-26 | Process | Approved
2.6 | BKDD02-ME-0D-03-007 | Process Flow Diagram (PFD) (New) | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-06-19 | 2020-06-19 | 396 | 2020-07-08 | wil | 2020-07-13 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-19 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | rep | 2020-11-25 | Process | Approved
2.7 | BKDD02-ME-0D-03-004D | Process Flow Diagram (PFD) (Update) Demolition | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-06-19 | 2020-06-19 | 372 | 2020-06-26 | wil | 2020-07-13 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-19 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2.8 | BKDD02-ME-0D-03-004 | Process Flow Diagram (PFD) (Update) Modification | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-06-19 | 2020-06-19 | 372 | 2020-06-26 | wil | 2020-07-13 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-19 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2.9 | BKDD02-ME-0D-08-009 | Utility Flow Diagram (UFD) Vent and Drain System (PLN) Modification | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-06-19 | 2020-06-19 | 372 | 2020-06-26 | wil | 2020-07-13 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-19 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,10 | BKDD02-ME-0D-08-009D | Utility Flow Diagram (UFD) Vent and Drain System (PLN) Demolition | 5 days | 0.8% |  | 2020-06-17 |  | 2020-07-10 | 2020-06-19 | 2020-06-19 | 372 | 2020-06-26 | wil | 2020-07-13 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-19 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
|  | Piping & Instrumentation Diagram (P&ID) | [24 empty] | Process
2,11 | BKDD06-ME-0D-05-002D | P&ID Sales Gas Metering Package (PLN) Demolition | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-19 | 2020-07-02 | 2020-07-02 | 372 | 2020-06-26 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,12 | BKDD06-ME-0D-06-001D | P&ID Vent and Drain (PLN) Demolition | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-19 | 2020-07-02 | 2020-07-02 | 396 | 2020-07-08 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,13 | BKDD06-ME-0D-06-002D | P&ID Nitrogen Package (PLN) Demolition | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-19 | 2020-07-02 | 2020-07-02 | 396 | 2020-07-08 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,14 | BKDD06-ME-0D-05-001D | P&ID Temporary Pig Receiver (PLN) Demolition | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-19 | 2020-07-02 | 2020-07-02 | 372 | 2020-06-26 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,15 | BKDD06-ME-0D-05-002 | P&ID Sales Gas Metering Package (PLN) Modification | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-19 | 2020-07-02 | 2020-07-02 | 372 | 2020-06-26 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,16 | BKDD06-ME-0D-06-001 | P&ID Vent and Drain (PLN) Modification | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-19 | 2020-07-02 | 2020-07-02 | 396 | 2020-07-08 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,17 | BKDD06-ME-0D-06-002 | P&ID Nitrogen Package (PLN) Modification | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-19 | 2020-07-02 | 2020-07-02 | 396 | 2020-07-08 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,18 | BKDD06-ME-0D-05-001 | P&ID Temporary Pig Receiver (PLN) Modification Incl. Pig Receiver | 10 days | 0.9% |  | 2020-06-17 |  | 2020-06-19 | 2020-07-02 | 2020-07-02 | 372 | 2020-06-26 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process | Approved
2,19 |  | P&ID Pig Receiver (combined into P&ID Temporary Pig Receiver) | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-26 | 2020-07-02 | 2020-07-02 | 396 | 2020-07-08 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | 530 | 2020-10-02 | Process
2,20 | BKDD06-ME-0D-06-003 | P&ID Seperator System Pigging Facility | 10 days | 0.8% |  | 2020-06-17 |  | 2020-06-26 | 2020-07-02 | 2020-07-02 | 396 | 2020-07-08 | wil | 2020-07-15 | 2020-07-23 | 2020-07-23 | 466 | 2020-08-13 | wil | 2020-08-26 | 505 | 2020-09-04 | 2020-09-24 | 2020-08-26 | rep | 2020-11-25 | Process | Approved
3 | PROCESS SAFETY | [25 empty] | ProSaf
3.1 | BKDD00-ME-0Q-70-003 | Fire Protection Philosophy (Update) | 5 days | 0.8% |  |  |  | 2020-07-21 | 2020-07-24 | 2020-07-24 | 443 | 2020-07-29 | don | 2020-09-12 | 2020-08-31 | 2020-08-07 | 569 | 2020-11-23 | kons | 2020-12-15 | x | x | 2020-09-25 | 2020-09-25 | 586 | 2020-12-17 | ProSaf | waiting for AFC approval
3.2 | BKDD06-ME-4D-49-006 | Fire & Gas Detector Layout Sales Gas Metering Area (Update) | 5 days | 0.8% |  | 2020-07-30 |  |  | 2020-08-07 | 2020-08-07 | 527 | 2020-10-08 | x | x | 2020-08-31 | 2020-08-21 | 581 | 2020-12-03 | kons | 2020-12-15 | x | x | 2020-10-09 | 2020-10-01 | 587 | 2020-12-17 | ProSaf | waiting for AFC approval
3.3 | BKDD02-ME-0Q-76-001 | Fire Fighting and Safety Equipment List (Update) | 5 days | 0.8% |  | 2020-07-30 |  | 2020-07-30 | 2020-08-07 | 2020-08-07 | 473 | 2020-08-07 | don | 2020-09-12 | 2020-08-31 | 2020-08-21 | 522 | 2020-09-30 | kons | 2020-12-15 | x | x | 2020-10-09 | 2020-10-01 | 586 | 2020-12-17 | ProSaf | waiting for AFC approval
3.4 | BKDD02-ME-0D-04-002 | Fire Fighting Equipment Layout (Update) | 5 days | 0.4% |  | 2020-07-30 |  | 2020-07-30 | 2020-08-07 | 2020-08-07 | 446 | 2020-07-30 | don | 2020-09-12 | 2020-08-31 | 2020-08-21 | 520 | 2020-09-29 | kons | 2020-12-15 | x | x | 2020-10-09 | 2020-10-01 | 587 | 2020-12-17 | ProSaf | waiting for AFC approval
3.5 | BKDD02-ME-0D-04-003 | Safety Equipment Layout | 5 days | 0.4% |  | 2020-07-30 |  | 2020-07-30 | 2020-08-07 | 2020-08-07 | 450 | 2020-08-05 | don | 2020-09-12 | 2020-08-31 | 2020-08-21 | 516 | 2020-09-25 | kons | 2020-12-15 | x | x | 2020-10-09 | 2020-10-01 | 587 | 2020-12-17 | ProSaf | waiting for AFC approval
3.6 | BKDD02-ME-0D-04-001 | Escape Route Layout | 5 days | 0.4% |  |  |  |  | 2020-08-07 | 2020-08-07 | 446 | 2020-07-30 | don | 2020-09-12 | 2020-08-31 | 2020-08-21 | 516 | 2020-09-25 | kons | 2020-12-15 | x | x | 2020-10-09 | 2020-10-01 | 587 | 2020-12-17 | ProSaf | waiting for AFC approval
3.7 | BKOP-BRU-0K-00-001 | Vent Dispersion Study |  | 0.8% |  |  |  |  | 2020-08-07 | 2020-08-07 | 514 | 2020-09-23 | x | x | 2020-08-31 | 2020-08-21 | 529 | 2020-10-08 | don | 2020-10-15 | 559 | 2020-11-05 | 2020-10-09 |  | 586 | 2020-12-17 | ProSaf | waiting for AFC approval
3.8 | BKDD00-ME-0L-72-001 | Fire Fighting and Safety Equipment Specification |  | 0.4% |  |  |  |  | 2020-08-07 | 2020-08-07 | 465 | 2020-08-13 | x | x | 2020-08-31 | 2020-08-21 | 569 | 2020-11-23 | kons | 2020-12-15 | x | x | 2020-10-09 | 2020-10-01 | 586 | 2020-12-17 | ProSaf | waiting for AFC approval
3.9 | BKDD02-ME-0Q-70-001 | Hazardous Area Classification Schedule | 5 days | 0.8% |  |  |  |  | 2020-07-17 | 2020-07-17 | 413 | 2020-07-14 | roy | 2020-07-29 | 2020-08-31 | 2020-07-31 | 520 | 2020-09-29 | kons | 2020-12-15 | x | x | 2020-10-09 | 2020-09-18 | 586 | 2020-12-17 | ProSaf | waiting for AFC approval
3.10, | BK06-BRU-0Q-00-001 | HAZOP & HAZID | 5 days | 1.9% |  |  |  | 2020-09-04 | 2020-09-10 | 2020-08-12 | done | 2020-09-08 | done | 2020-09-08 | 2020-09-10 | x | done | 2020-09-08 | done | 2020-09-10 | x | x | 2020-09-10 | x | done | 2020-09-10 | ProSaf | waiting for AFC approval
3.11, | BK06-BRU-0Q-00-002~1 | HAZOP Study Report | 15 days | 0.75% |  |  |  |  | 2020-09-17 | 2020-08-28 | 509 | 2020-09-18 | wil | 2020-09-30 | 2020-10-01 | 2020-09-11 | 515 | 2020-10-01 | wil | 2020-10-20 | x | x | 2020-10-08 | 2020-09-18 | 552 | 2020-10-23 | ProSaf | waiting for AFC approval
3.12 | BK06-BRU-0Q-00-002~2 | HAZID Study Report | 15 days | 0.75% |  |  |  |  | 2020-09-24 | 2020-08-28 | 509 | 2020-09-18 | dit | 2020-09-30 | 2020-10-08 | 2020-09-11 | 543 | 2020-10-20 | kons | 2020-12-15 | x | x | 2020-10-08 |  | 589 | 2020-12-18 | ProSaf | waiting for AFC approval
3.14 | BK06-BRU-0Q-00-003~1 | HAZOP Closed Out Report | 15 days | 0.75% |  |  |  | 2020-10-09 | 2020-09-24 | 2020-09-15 | 552 | 2020-10-23 | wil | 2020-11-17 | 2020-10-08 | 2020-09-29 | 589 | 2020-12-18 | wil | 2021-12-02 | x | x | 2020-10-15 | 2020-10-01 | 606 | 2021-02-18 | ProSaf | Approved
3.15 | BK06-BRU-0Q-00-003~2 | HAZID Closed Out Report | 15 days | 0.75% |  |  |  | 2020-10-09 | 2020-10-01 | 2020-09-15 | 552 | 2020-10-23 | kons | 2020-12-15 | 2020-10-15 | 2020-09-29 | 589 | 2020-12-18 |  |  |  |  | 2020-10-15 | 2020-10-01 |  |  | ProSaf | waiting for IFA Review
4 | INSTRUMENT | [25 empty] | Instrument
4.1 | BKDD00-ME-4D-87-003 | Instrument ESD I/O List | 2 days | 0.8% |  |  |  |  | 2020-07-06 | 2020-07-06 | 402 | 2020-07-10 | roy | by wa | 2020-07-20 | 2020-07-20 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-09-25 | 2020-09-07 | 538 | 2020-10-15 | Instrument | Approved
4.2 | BK06-BRU-4U-40-001 | Instrument Index | 2 days | 0.8% |  |  |  |  | 2020-07-06 | 2020-07-06 | 402 | 2020-07-10 | roy | by wa | 2020-07-20 | 2020-07-20 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-09-25 | 2020-09-07 | 540 | 2020-10-19 | Instrument | Approved
4.3 | BKDD00-ME-4O-87-007 | Instrument Tubing Schedule |  | 0% |  |  |  |  | 2020-07-06 | 2020-07-06 | 523 | 2020-09-30 | roy | 2020-11-10 | 2020-07-20 | 2020-07-20 | 574 | 2020-11-25 | roy | 2020-11-26 | x | x | 2020-09-25 | 2020-09-07 | 579 | 2020-12-01 | Instrument | Approved
4.4 | BKDD00-ME-4O-87-006 | Instrument Cable Schedule | 2 days | 1.4% |  |  |  |  | 2020-07-07 | 2020-07-07 | 422 | 2020-07-17 | roy | 2020-07-20 | 2020-07-21 | 2020-07-21 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-09-25 | 2020-09-08 | 549 | 2020-10-23 | Instrument | Approved
4.5 | BKDD00-ME-4D-43-006 | Instrument Cable Block Diagram | 2 days | 0.8% |  |  |  |  | 2020-07-07 | 2020-07-07 | 422 | 2020-07-17 | roy | 2020-07-20 | 2020-07-21 | 2020-07-21 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-09-25 | 2020-09-08 | 549 | 2020-10-23 | Instrument | Approved
4.6 | BK06-BRU-4D-41-001 | Cause & Effect Matrix | 2 days | 0.8% |  |  |  |  | 2020-07-09 | 2020-07-09 | 402 | 2020-07-10 | roy | by wa | 2020-07-23 | 2020-07-23 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-09-25 | 2020-09-10 | 546 | 2020-10-23 | Instrument | Approved
4.6 | BK06-BRU-4J-00-001 | PSV Calculation* | 2 days | [5 empty] | 2020-07-09 | 2020-07-09 |  |  |  |  | 2020-07-23 | 2020-07-23 | [6 empty] | 2020-09-10 | 2020-09-10 |  |  | Instrument | Approved
4.7 | BK06-BRU-4M-00-001 | Datasheet for Pressure Regulator Valve | 2 days | 0.8% |  |  |  | 2020-07-10 | 2020-07-08 | 2020-07-08 | 419 | 2020-07-16 | roy | 2020-06-25 | 2020-09-04 | 2020-07-22 | 506 | 2020-09-04 |  |  |  |  | 2020-10-08 | 2020-09-09 |  | x | Instrument | Approved
4.8 | BK06-BRU-4M-00-002 | Datasheet for Pressure Gauge | 2 days | 0.8% |  |  |  | 2020-07-10 | 2020-07-08 | 2020-07-08 | 402 | 2020-07-10 | roy | 2020-07-29 | 2020-07-22 | 2020-07-22 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-10-08 | 2020-09-09 | 542 | 2020-10-20 | Instrument | Approved
4.9 | BK06-BRU-4M-00-003 | Datasheet for On/Off Valve | 2 days | 0.8% |  |  |  | 2020-07-10 | 2020-07-08 | 2020-07-08 | 472 | 2020-08-14 | roy | 2020-08-24 | 2020-09-04 | 2020-07-22 | 506 | 2020-09-04 | roy | 2020-11-10 | 568 | 2020-11-19 | 2020-10-08 | 2020-09-09 | 582 | 2020-12-08 | Instrument | Approved
4.10, | BK06-BRU-4M-00-004 | Datasheet for PSV | 2 days | 0.8% |  |  |  |  | 2020-07-13 | 2020-07-13 | 419 | 2020-07-16 | roy | 2020-06-25 | 2020-08-31 | 2020-07-27 | 506 | 2020-09-04 | x | x | x | x | 2020-10-08 | 2020-09-14 | 568 | 2020-11-19 | Instrument | Approved
4.11 | BK06-BRU-4M-00-005 | Datasheet for Level Switch | 2 days | 0.8% |  |  |  |  | 2020-07-13 | 2020-07-13 | 472 | 2020-08-14 | roy | 2020-08-24 | 2020-09-04 | 2020-07-27 | 506 | 2020-09-04 | roy | 2020-11-10 | 571 | 2020-11-23 | 2020-10-08 | 2020-09-14 | 579 | 2020-12-01 | Instrument | Approved
4.12 | BK06-BRU-4M-00-006 | Datasheet for Shutdown Valve | 2 days | 0.8% |  |  |  |  | 2020-07-13 | 2020-07-13 | 402 | 2020-07-10 | roy | 2020-06-25 | 2020-09-04 | 2020-07-27 | 506 | 2020-09-04 | roy | 2020-11-10 | x | x | 2020-10-08 | 2020-09-14 | 568 | 2020-11-19 | Instrument | Approved
4.13 | BK06-BRU-4M-00-007 | Datasheet for F&G Detector | 2 days | 0.8% |  |  |  | 2020-08-28 | 2020-09-04 | 2020-07-13 | x | deleted | x | x | 2020-09-18 | 2020-07-27 | x | deleted | x | x | x | x | 2020-10-08 | 2020-09-14 | x | deleted | Instrument | Approved
4.14 | BK06-BRU-4M-00-008 | Datasheet for Level Gauge | 2 days | 0.8% |  |  |  |  | 2020-07-13 | 2020-07-13 | 424 | 2020-07-17 | roy | by wa | 2020-07-27 | 2020-07-27 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-10-08 | 2020-09-14 | 540 | 2020-10-19 | Instrument | Approved
4.15 | BK06-BRU-4M-00-009 | Datasheet for Pig Indicator | 3 days | 1.4% |  |  |  |  | 2020-07-13 | 2020-07-13 | 402 | 2020-07-10 | roy | 2020-06-25 | 2020-08-31 | 2020-07-27 | 506 | 2020-09-04 | roy | 2020-11-10 | x | x | 2020-10-08 | 2020-09-14 | 566 | 2020-11-13 | Instrument | Approved
4.16 | BKDD06-ME-4D-49-003 | Instrument Location Layout (Update) | 2 days | 1.4% |  |  |  | 2020-08-28 | 2020-09-04 | 2020-07-23 | 503 | 2020-09-02 | roy | 2020-11-10 | 2020-09-18 | 2020-08-06 | 566 | 2020-11-13 | roy | 2020-11-14 | x | x | 2020-10-09 | 2020-09-24 | 578 | 2020-11-27 | Instrument | Approved
4.18 | BK06-BRU-4D-45-001 | Instrument Hookup Drawing | 2 days | 1.4% |  |  |  |  | 2020-07-23 | 2020-07-23 | 402 | 2020-07-10 | roy | by wa | 2020-08-06 | 2020-08-06 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-10-09 | 2020-09-24 | 568 | 2020-11-19 | Instrument | Approved
4.19 | BK06-BRU-4D-43-002 | Instrument Loop Diagram | 3 days | 1.4% |  |  |  |  | 2020-07-30 | 2020-07-30 | 409 | 2020-07-14 | roy | 2020-07-29 | 2020-08-13 | 2020-08-13 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-10-09 | 2020-10-01 | 540 | 2020-10-19 | Instrument | Approved
4.20, | 011-BKDD06-4D-001 | Wiring & Termination Diagram - PLN - SIS Panel 87-RCS-003 (ESD) | 2 days | 1.4% |  |  |  |  | 2020-08-05 | 2020-08-05 | 437 | 2020-07-23 | roy | 2020-06-25 | 2020-09-04 | 2020-08-19 | 538 | 2020-10-15 | x | x | x | x | 2020-10-10 | 2020-10-01 | 580 | 2020-12-03 | Instrument | Approved
4.21 | BKDD06-ME-4D-49-003 | Cable Layout (Update) | 2 days | 1.4% |  |  |  | 2020-08-28 | 2020-09-04 | 2020-08-12 | x | combined | x | x | 2020-09-18 | 2020-08-26 | x | combined | x | x | x | x | 2020-10-10 | 2020-10-01 | x | combined | Instrument | Approved
4.22 | update | F&G Layout (Update) | 3 days | 0% | [5 empty] | 2020-08-14 |  | moved |  |  |  | 2020-08-28 |  | moved | [7 empty] | moved | Instrument | Approved
4,21 | BKDD00-ME-4D-49-027 | Instrument Air (Nitrogen) Supply Layout |  | 1.4% |  |  |  |  | 2020-08-05 | 2020-08-19 | 523 | 2020-09-30 | roy | 2020-11-10 | 2020-09-04 | 2020-09-02 | 574 | 2020-11-25 | roy | 2020-11-26 | x | x | 2020-10-10 |  | 578 | 2020-11-27 | Instrument | Approved
4,22 | BKDD06-ME-4D-49-009 | Instrument JB, Cable Tray Routing | 3 days | 0.8% |  |  |  | 2020-08-28 | 2020-09-04 | 2020-08-19 | 502 | 2020-09-04 | roy | 2020-11-10 | 2020-09-18 | 2020-09-02 | 571 | 2020-11-23 | roy | 2020-11-24 | x | x | 2020-10-10 | 2020-10-01 | 576 | 2020-11-26 | Instrument | Approved
4,23 | BK06-BRU-4D-45-002 | Installation Detail Layout & JB General Arrangement Drawing | 3 days | 0.8% |  |  |  |  | 2020-08-24 | 2020-08-24 | 422 | 2020-07-17 | roy | 2020-07-20 | 2020-09-07 | 2020-09-07 | 468 | 2020-08-14 | roy | 2020-08-24 | x | x | 2020-10-10 | 2020-10-01 | 545 | 2020-10-22 | Instrument | Approved
4,24 | BK06-BRU-4MT-47-001 | MTO for Instrument | 3 days | 1.6% |  |  |  | 2020-08-28 | 2020-09-11 | 2020-08-27 | 523 | 2020-09-30 | x | x | 2020-09-25 | 2020-09-10 | 576 | 2020-11-26 | roy | 2020-11-27 | x | x | 2020-10-15 | 2020-10-02 | 580 | 2020-12-03 | Instrument | Approved
5 | ELECTRICAL | [25 empty] | Electrical
5.1 | BK06-BRU-3D-32-001 | Single Line Diagram | 5 days | 1.4% |  |  |  |  | 2020-07-09 | 2020-07-09 | 417 | 2020-07-15 | roy | 2020-07-20 | 2020-07-23 | 2020-07-23 | 464 | 2020-08-14 | roy | 2020-08-28 | x | x | 2020-09-24 | 2020-08-06 | 526 | 2020-10-06 | Electrical | Approved
5.2 | BK06-BRU-3M-88-001 | Lighting Fixture Datasheet | 2 days | 0.8% |  |  |  |  | 2020-07-13 | 2020-07-13 | 395 | 2020-07-08 | roy | 2020-07-29 | 2020-07-27 | 2020-07-27 | 458 | 2020-08-10 | roy | 2020-08-28 | x | x | 2020-09-24 | 2020-08-10 | 518 | 2020-09-29 | Electrical | Approved
5.3 | BK06-BRU-3D-37-001 | Lightning Protection Detail Drawing | 3 days | 1.4% |  |  |  |  | 2020-07-16 | 2020-07-16 | 413 | 2020-07-14 | roy | 2020-07-29 | 2020-07-30 | 2020-07-30 | 458 | 2020-08-10 | roy | 2020-08-28 | x | x | 2020-09-24 | 2020-08-13 | 511 | 2020-09-22 | Electrical | Approved
5.4 | BK06-BRU-3D-37-002 | Grounding Detail Drawing | 3 days | 1.4% |  |  |  |  | 2020-07-21 | 2020-07-21 | 399 | 2020-07-10 | roy | 2020-07-29 | 2020-08-04 | 2020-08-04 | 458 | 2020-08-10 | roy | 2020-08-28 | x | x | 2020-09-24 | 2020-08-18 | 511 | 2020-09-22 | Electrical | Approved
5.5 | BK06-BRU-3D-31-001 | Hazardous Area Classification |  | 0.8% |  |  |  |  | 2020-07-27 | 2020-07-27 | 434 | 2020-07-22 | roy | by wa | 2020-08-10 | 2020-08-10 | x | 2020-08-11 | x | x | x | x | 2020-09-28 | 2020-08-24 | 560 | 2020-11-05 | Electrical | Approved
5.6 | BK06-BRU-3D-37-003 | Lighting Layout | 3 days | 1.4% |  |  |  |  | 2020-08-13 | 2020-08-13 | 424 | 2020-07-17 | roy | by wa | 2020-08-27 | 2020-08-27 | 460 | 2020-08-14 | roy | 2020-08-28 | x | x | 2020-09-28 | 2020-09-10 | 560 | 2020-11-05 | Electrical | Approved
5.7 | BK06-BRU-3D-37-004 | Grounding Layout | 3 days | 1.4% |  |  |  |  | 2020-08-19 | 2020-08-19 | 424 | 2020-07-17 | roy | by wa | 2020-09-02 | 2020-09-02 | 460 | 2020-08-14 | roy | 2020-08-28 | x | x | 2020-09-28 | 2020-09-16 | 593 | 2020-11-09 | Electrical | Approved
5.8 | BK06-BRU-3D-37-005 | Lightning Protection Layout | 3 days | 1.4% |  |  |  |  | 2020-08-25 | 2020-08-25 | 421 | 2020-07-16 | roy | 2020-07-20 | 2020-09-08 | 2020-09-08 | 460 | 2020-08-14 | x | x | x | x | 2020-09-28 | 2020-09-22 | 593 | 2020-11-09 | Electrical | Approved
5.9 | BK06-BRU-3D-37-006 | Electrical General Arrangement | 3 days | 1.4% |  |  |  |  | 2020-08-28 | 2020-08-28 | 437 | 2020-07-23 | roy | by wa | 2020-09-11 | 2020-09-11 | 464 | 2020-08-14 | roy | 2020-08-28 | x | x | 2020-09-28 | 2020-09-25 | 511 | 2020-09-22 | Electrical | Approved
5.10. | BK06-BRU-3MT-38-001 | MTO for Electrical | 3 days | 1.4% |  | 2020-07-30 |  |  | 2020-09-02 | 2020-09-02 | 460 | 2020-08-14 | roy | 2020-08-28 | 2020-08-28 | 2020-09-16 | 508 | 2020-09-04 | x | x | x | x | 2020-09-30 | 2020-09-30 | 567 | 2020-11-19 | Electrical | Approved
6 | PIPING | [25 empty] | Piping
6.1 | BK06-BRU-1U-00-001 | Tie-in Points List | 1 day | 0.4% |  |  |  | 2020-07-10 | 2020-07-06 | 2020-07-06 | 467 | 2020-08-14 | dit | 2020-08-18 | 2020-08-31 | 2020-07-20 | 507 | 2020-09-16 | dit | 2020-09-17 | x | x | 2020-09-25 | 2020-08-03 | rep | 2020-12-22 | Piping | Approved
6.2 | BKDD00-ME-1Q-00-004 | Critical Line List (Update) | 2 days | 0.8% |  |  |  | 2020-07-10 | 2020-07-06 | 2020-07-06 | 411 | 2020-07-14 | dit | 2020-08-03 | 2020-07-20 | 2020-07-20 | 467 | 2020-08-14 | dit | 2020-08-18 | x | x | 2020-09-25 | 2020-08-03 | 557 | 2020-11-05 | Piping | Approved
6.3 | BK06-BRU-1U-00-003 | List of Piping Specialty Item | 2 days | 0.8% |  |  |  |  | 2020-07-08 | 2020-07-08 | 411 | 2020-07-14 | dit | 2020-08-03 | 2020-07-22 | 2020-07-22 | 467 | 2020-08-14 | dit | 2020-08-18 | x | x | 2020-09-25 | 2020-08-05 | rep | 2020-12-22 | Piping | Approved
6.4 | BK06-BRU-1M-00-001 | Datasheet for Manual Valves | 2 days | 0.4% |  |  |  |  | 2020-07-15 | 2020-07-15 | 428 | 2020-07-17 | dit | 2020-07-27 | 2020-08-31 | 2020-07-29 | 507 | 2020-09-16 | dit | 2020-09-19 | x | x | 2020-09-28 | 2020-08-12 | rep | 2020-12-23 | Piping | Approved
6.5 | BK06-BRU-1M-00-002 | Datasheet for Piping Specialty Item | 5 days | 1.4% |  |  |  | 2020-07-24 | 2020-07-15 | 2020-07-15 | 451 | 2020-08-05 | dit | 2020-08-10 | 2020-08-31 | 2020-07-29 | 554 | 2020-11-02 | dit | 2020-11-09 | 590 | 2020-12-22 | 2020-09-28 | 2020-08-12 | 593 | 2020-12-23 | Piping | Approved
6.6 | BKDD06-ME-1D-11-001 | PLN Area Equipment Layout | 5 days | 3% |  |  |  |  | 2020-07-20 | 2020-07-20 | 420 | 2020-07-16 | dit | 2020-07-23 | 2020-08-03 | 2020-08-03 | 455 | 2020-08-10 | dit | 2020-08-14 | 496 | 2020-08-31 | 2020-09-28 | 2020-08-17 | rep2 | 2020-12-16 | Piping | Approved
6.7 | BKDD06-ME-1D-11 | Piping Plan (Update) | 1 day | 4.2% |  | 2020-07-24 |  | 2020-08-14 | 2020-08-28 | 2020-08-03 | 496 | 2020-08-28 | dit | 2020-09-13 | 2020-09-09 | 2020-08-17 | 532 | 2020-10-09 | dit | 2020-10-21 | 554 | 2020-11-02 | 2020-10-02 | 2020-08-31 | re2 | 2020-12-22 | Piping | Approved
6.8 | BK06-BRU-1D-17-001 | Piping Isometrics | 5 days | 4.6% |  | 2020-08-28 |  | 2020-09-04 | 2020-09-04 | 2020-08-12 | 532 | 2020-10-09 | dit | 2020-10-15 | 2020-09-10 | 2020-08-26 | 554 | 2020-11-02 | dit | 2020-12-10 | x | x | 2020-10-07 | 2020-09-09 | rep1 | 2020-12-22 | Piping | Approved
6.9 | BK06-BRU-1J-00-001 | Piping Stress Analysis | 5 days | 1.4% |  | 2020-09-04 |  | 2020-10-09 | 2020-09-18 | 2020-08-24 | 548 | 2020-10-23 | dit | 2020-11-18 | 2020-10-02 | 2020-09-07 | 570 | 2020-11-23 | dit | 2020-12-10 | x | x | 2020-10-09 | 2020-09-21 | 593 | 2020-12-29 | Piping | Approved
6.10, | BK06-BRU-1D-12-001 | Pipe Support Drawing | 3 days | 1.4% |  | 2020-09-04 |  |  | 2020-09-11 | 2020-08-21 | 532 | 2020-10-09 | dit | 2020-10-21 | 2020-09-18 | 2020-09-04 | 564 | 2020-11-09 | dit | 2020-12-15 | x | x | 2020-09-28 | 2020-09-18 | rep | 2021-01-21 | Piping | Approved
6.11 | BK06-BRU-1MT-00-001 | MTO for Manual Valve | 3 days | 0.8% |  |  |  |  | 2020-08-25 | 2020-08-25 | 415 | 2020-07-15 | dit | 2020-11-03 | 2020-09-11 | 2020-09-08 | 507 | 2020-09-16 | dit | 2020-09-22 | x | x | 2020-10-09 | 2020-09-22 | 554 | 2020-11-02 | Piping | Approved
6.12 | BK06-BRU-1MT-00-002 | MTO for Piping | 3 days | 0.8% |  |  |  |  | 2020-09-11 | 2020-08-26 | 536 | 2020-10-14 | dit | 2020-11-04 | 2020-09-25 | 2020-09-09 | 562 | 2020-11-06 | dit | 2020-12-10 | x | x | 2020-10-09 | 2020-09-23 | rep | 2020-12-22 | Piping | Approved
7 | MECHANICAL | [25 empty] | Mechanical
7.1 | BK06-BRU-1U-00-004 | Equipment List (Update) | 2 days | 1.8% |  |  |  | 2020-07-10 | 2020-07-06 | 2020-07-06 | 444 | 2020-07-30 | dit | 2020-07-30 | 2020-09-04 | 2020-07-20 | 554 | 2020-11-02 | dit | 2020-11-04 | x | x | 2020-09-28 | 2020-08-03 | rep | 2020-12-18 | Mechanical | Approved
7.2 | BK06-BRU-1M-00-003 | Datasheet for Separator | 3 days | 0.8% |  |  |  | 2020-07-10 | 2020-07-09 | 2020-07-09 | 444 | 2020-07-30 | dit | 2020-08-29 | 2020-09-04 | 2020-07-23 | 507 | 2020-09-16 | dit | 2020-09-19 | 551 | 2020-10-23 | 2020-09-28 | 2020-08-06 | 565 | 2020-11-12 | Mechanical | Approved
7.3 | BK06-BRU-1M-00-004 | Datasheet for Tank | 3 days | 0.8% |  |  |  | 2020-07-10 | 2020-07-14 | 2020-07-14 | 444 | 2020-07-30 | dit | 2020-08-29 | 2020-09-04 | 2020-07-28 | 507 | 2020-09-16 | dit | 2020-09-19 | 551 | 2020-10-23 | 2020-09-28 | 2020-08-11 | 565 | 2020-11-12 | Mechanical | Approved
7.4 | BK06-BRU-1M-00-005 | Datasheet for Pig Receiver | 3 days | 0.8% |  |  |  | 2020-07-21 | 2020-07-17 | 2020-07-17 | 444 | 2020-07-30 | dit | 2020-07-30 | 2020-09-04 | 2020-07-31 | 507 | 2020-09-16 | dit | 2020-09-17 | x | x | 2020-09-28 | 2020-08-14 | rep2 | 2020-12-18 | Mechanical | Approved
7.5 | BK06-BRU-1M-00-006 | Datasheet for Portable Drain Pump | 3 days | 0.8% |  | 2020-07-24 |  |  | 2020-07-22 | 2020-07-22 |  | del |  |  | 2020-08-05 | 2020-08-05 |  | del |  |  |  |  | 2020-08-19 | 2020-08-19 |  | del
8 | CIVIL | [25 empty] | Civil
8.1 | BK06-BRU-6J-00-001 | Calculation for Separator and Tank Foundation | 3 days | 1.4% |  | 2020-07-24 |  | 2020-08-07 | 2020-07-14 | 2020-07-14 | 453 | 2020-08-07 | x | x | 2020-09-11 | 2020-07-28 | 533 | 2020-10-09 | kons | 2020-12-15 | x | x | 2020-10-02 | 2020-08-11 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.2 | BK06-BRU-6J-00-002 | Calculation for Bundwall | 3 days | 1.4% |  | 2020-07-24 |  | 2020-08-07 | 2020-07-17 | 2020-07-17 | 475 | 2020-08-18 | x | x | 2020-09-11 | 2020-07-31 | 533 | 2020-10-09 | kons | 2020-12-15 | x | x | 2020-10-02 | 2020-08-14 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.3 | BK06-BRU-6J-00-003 | Calculation for Pipe Support Foundation | 3 days | 1.4% |  | 2020-07-24 |  | 2020-08-07 | 2020-10-13 | 2020-08-26 | 533 | 2020-10-09 | x | x | 2020-09-14 | 2020-09-09 | 553 | 2020-10-27 | kons | 2020-12-15 | x | x | 2020-10-05 | 2020-09-23 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.4 | BK06-BRU-6J-00-004 | Calculation for Pig Receiver Foundation |  | 0% |  | 2020-08-03 |  | 2020-08-07 | 2020-08-26 | 2020-08-26 | 453 | 2020-08-07 | x | x | 2020-09-14 | 2020-09-09 | 541 | 2020-10-19 | kons | 2020-12-15 | x | x | 2020-10-05 | 2020-09-23 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.5 | BK06-BRU-6D-6C-001 | Separator and Tank Foundation Drawing | 5 days | 1.2% |  | 2020-07-30 |  | 2020-08-07 | 2020-07-21 | 2020-07-21 | 471 | 2020-08-14 | x | x | 2020-09-14 | 2020-08-04 | 533 | 2020-10-09 | kons | 2020-12-15 | x | x | 2020-10-05 | 2020-08-18 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.6 | BK06-BRU-6D-6C-002 | Bundwall Drawing | 5 days | 1.2% |  | 2020-07-30 |  | 2020-08-07 | 2020-07-24 | 2020-07-24 | 477 | 2020-08-19 | x | x | 2020-09-14 | 2020-08-07 | 533 | 2020-10-09 | kons | 2020-12-15 | x | x | 2020-10-05 | 2020-08-21 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.7 | BK06-BRU-6D-6C-003 | Pipe Support Foundation Drawing | 5 days | 1.2% |  | 2020-07-30 |  | 2020-08-07 | 2020-09-18 | 2020-09-02 | 539 | 2020-10-15 | x | x | 2020-09-21 | 2020-09-16 | 550 | 2020-10-23 | kons | 2020-12-15 | x | x | 2020-10-05 | 2020-09-30 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.8 | BK06-BRU-6D-6C-004 | Pig Receiver Foundation Drawing |  | 0% |  | 2020-08-03 |  | 2020-08-07 | 2020-09-02 | 2020-09-02 | 493 | 2020-08-26 | x | x | 2020-09-21 | 2020-09-16 | 515 | 2020-09-24 | kons | 2020-12-15 | x | x | 2020-10-05 | 2020-09-30 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.9 | BK06-BRU-6D-68-001 | Grounding Box Drawing | 5 days | 1.2% |  | 2020-07-30 |  | 2020-08-13 | 2020-08-27 | 2020-08-27 | 477 | 2020-08-19 | x | x | 2020-09-14 | 2020-09-10 | 544 | 2020-10-22 | kons | 2020-12-15 | x | x | 2020-09-28 | 2020-09-24 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.10, | BK06-BRU-6D-63-001 | Lighting Support Drawing | 5 days | 1.2% |  | 2020-07-30 |  | 2020-08-13 | 2020-08-24 | 2020-08-24 | 477 | 2020-08-19 | x | x | 2020-09-14 | 2020-09-07 | 515 | 2020-09-24 | kons | 2020-12-15 | x | x | 2020-09-28 | 2020-09-21 | 588 | 2020-12-17 | Civil | waiting for AFC approval
8.11 | BK06-BRU-6MT-00-001 | MTO for Civil |  | 0% |  |  |  | 2020-10-09 | 2020-10-13 | 2020-08-28 | 533 | 2020-10-09 | x | x | 2020-09-25 | 2020-09-11 | 550 | 2020-10-23 | kons | 2020-12-15 | x | x | 2020-10-09 | 2020-09-25 | 596 | 2021-01-08 | Civil | waiting for AFC approval
Total |  |  |  | 100%
*Text in blue color indicates additional deliverable
Formulas:
Issued for Approval (IFA) = [Issued for Review (IFR)]+14
Issued for Approval (IFA) = [Issued for Approval (IFA), row below]
Approved for Construction (AFC) = [Issued for Approval (IFA)]+14
Issued for Review (IFR) = [Issued for Review (IFR), row above]+7
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Digabung atasnya
Note on R93: user: RE IFA 496
Note on S93: user: Re-IFA 31 Agustus 20